## HME
ANNUAL ACTION PLAN FOR THE YEAR 2019-20 UNDER BORDER UNDER BORDER AREA DEVELOPMENT PROGRAMME (Health & Medical Education Department)
S. No. | Name of the work/project/scheme | Project Type (New/Ongoing) | District | Block | village | Distance from IB/LOC kms. | Sector | Estimated Cost | Year of comencement (MM/YYYY) | Target for completion (MM/YYY/ | Cum expdt incl USB 3/2019 | Allocation 2019-20
[12 empty] | CS | SS | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Sub-Centre Kaneri Block Akhnoor, Jammu | Ongoing | Jammu | Akhnoor | Kaneri | 10 km | HEALTH | 63.65 | 2011-12 | 2019-20 | 62.4 | 1.12 | 0.13 | 1.25
2 | Construction of Sub-Centre Gharana Block R. S. Pura, Jammu. | Ongoing | Jammu | R.S.Pura | Gharana | 1 km | HEALTH | 62.3 | 2012-13 | 2019-20 | 58.32 | 3.58 | 0.4 | 3.98
3 | Construction of Sub-Centre Pangdour, Samba District | Ongoing | Samba | Samba | Pangdour | 4 km | HEALTH | 60.65 | 2012-13 | 2019-20 | 59.85 | 0.72 | 0.08 | 0.8
4 | Construction of Sub-Centre Chann Morian Block Hiranagar, Kathua District. | Ongoing | Kathua | Hiranagar | Chann Morian | 8 km | HEALTH | 57.3 | 2012-13 | completed | 55.71 | 1.44 | 0.15 | 1.59
5 | Construction of Sub-Centre Dharathi Block Mendhar, Poonch. | Ongoing | Poonch | Mendhar | Dharathi | 1 km | HEALTH | 94.73 | 2011-12 | 2019-20 | 89.68 | 4.54 | 0.51 | 5.05
6 | Const. of Sub-Centre Dhara Dullian, Poonch District | Ongoing | Poonch | Poonch | Dhara Dullian | 2 km | HEALTH | 94.73 | 2015-16 | 2019-20 | 89.7 | 4.53 | 0.5 | 5.03
7 | Construction of Sub-Centre Marg Hayatpura, Rajouri District | Ongoing | Rajouri | Manjakote | Marg Hayatpura | 2 Km | HEALTH | 66.43 | 2012-13 | 2019-20 | 64.33 | 1.89 | 0.21 | 2.1
8 | Const. of NTPHC Sair Makri Nowshera, Rajouri District | Ongoing | Rajouri | Nowshera | Sair Makri | 1 km | HEALTH | 55 | 2015-16 | 2019-20 | 52.95 | 1.85 | 0.2 | 2.05
9 | Const. of 30 bedded IPD Block at SDH Dawar Gurez | Ongoing | Bandipora | Gurez | Dawar | 5 Km | HEALTH | 713 | 2014 | 2021-22 | 278.35 | 78.91 | 8.77 | 87.68
| G.Total | [10 empty] | 98.58 | 10.95 | 109.53