## Jammu
Annual Action Plan under BADP for the year 2019-20 in respect of Jammu-District
S. No. | Name of the work/Project/Scheme | Ongoing/New | District | Block | Village | Distance from IB/LOC (Kms) | Sector | Est. Cost | Year of Commencement (MM/YY) | Target for completion (MM/YY) | Cum Expdt. incl USB 03/2019 | Allocation 2019-20
[12 empty] | Central Share | State Share | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 119
1 | Constructionof link road from Dukhada to Radha Swami Ashram via Makara | Ongoing | Jammu | Akhnoor | Dukhada, Makara | 7 | INFRA- I | 204 | 2005-06 | 2022-23 | 107.03 | 8.05 | 0.89 | 8.94 |  | 335.91
2 | Construction of road from Dhok Khalsa to Kali Bari (cost overrun) | Ongoing | Jammu | Akhnoor | Dhok Khalsa , Kali Bari | 8 | INFRA- I | 89 | 2005-06 | 2019-20 | 74.41 | 13.13 | 1.46 | 14.59 |  | 200.59
3 | Constructionof road from main road to Kote Gari via middle School to House of Madan Lal & allied links | Ongoing | Jammu | Akhnoor | Kote Gari | 2.5 | INFRA- I | 108 | 2002-03 | 2021-22 | 55.03 | 8.1 | 0.9 | 9 |  | 183.53
4 | Construction of link road from Saloori to Mohalla Romesh Lal on Ghar Majoor road | Ongoing | Jammu | Akhnoor | Ghar Majoor | 9 | INFRA- I | 45 | 2012-13 | 2020-21 | 27.66 | 5.4 | 0.6 | 6 |  | 93.66
5 | Construction of link road from Plouri to Moh. Varym Singh to Vidhuwali Sungal | Ongoing | Jammu | Akhnoor | Sungal | 7 | INFRA- I | 48.7 | 2012-13 | 2020-21 | 15.36 | 8.1 | 0.9 | 9 |  | 89.06
6 | Construction of lane/drain at W.no 2,3,4 from Bharda to Sathar at Bharda kalan | Ongoing | Jammu | Akhnoor | Bharda kalan | 7 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 19
7 | Construction of lane/drain from main road to the H/o Subash singh at Gurha Brahmana East | Ongoing | Jammu | Akhnoor | Gurha Brahmana East | 10 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 22
8 | Construction of lane/drain at Pakhiwala from the main road to the H/o Sh. Parkash singh at W.no 7 | Ongoing | Jammu | Akhnoor | Sungal lower A | 10 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 22
9 | Construction of road by laying of RBM from Shiv mandir Bharda kalan to Karala mohalla | Ongoing | Jammu | Akhnoor | Bharda kalan | 7 | INFRA- I | 7 | 2018-19 | 2019-20 | 3 | 3.6 | 0.4 | 4 |  | 25
10 | Instll. Of Shallow Hand Pumps (Non Potable) | Ongoing | Jammu | Akhnoor | Garkhal | 1 | SOCIAL | 11 | 2016-17 | 2019-20 | 9 | 1.8 | 0.2 | 2 |  | 25
11 | Repair/Renovation of HS Kotgarhi | Ongoing | Jammu | Akhnoor | Kot Garhi | 0-5 | EDUCATION | 6 | 2018-19 | 2019-20 | 2.3 | 3.33 | 0.37 | 3.7 |  | 15.7
12 | Balance work for Extension of Emergency/ Causality room and Construction of attached bathroom and Extension of Ultrasound room and Grill & Window ventilation of Stores at SDH Akhnoor (On going). | Ongoing | Jammu | Akhnoor | Akhnoor | 9 | HEALTH | 5 | 2018-19 | 2019-20 | 1.89 | 2.799 | 0.311 | 3.11 |  | 22.11
13 | Creation of 63 KVA S/Stn. at Chak Colony and Nai Basti (Devipur) alongwith HT & LT line | New | Jammu | Akhnoor | Chak Colony and Nai Basti (Devipur) | 0-7 | SOCIAL | 10 | 2019-20 | 2019-20 | 0 | 9 | 1 | 10 |  | 30
14 | Construction of Community Hall at Trewa | Ongoing | Jammu | Arnia | Trewa | 1.5 | SOCIAL | 20 | 2018-19 | 2020-21 | 5 | 3.6 | 0.4 | 4 |  | 34.5
15 | Construction of Bedminton Hall at alrady existing Statidum at Arnia | Ongoing | Jammu | Arnia | Changia | 1.5 | SPORTS | 15 | 2018-19 | 2020-21 | 4 | 2.7 | 0.3 | 3 |  | 26.5
16 | Construction of Land/ Drain from h/o Baldev Raj to Mandir at village Kotla | Ongoing | Jammu | Arnia | Trewa | 1.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13.5
17 | Consst. of Land/ Drain from h/o Ashok kumar to h/o chiman at village Kotla Trewa | Ongoing | Jammu | Arnia | Trewa | 1.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13.5
18 | Consst. of Land/ Drain near MS at Kaku- de-kothey | Ongoing | Jammu | Arnia | Allah | 2 | INFRA- I | 6 | 2018-19 | 2019-20 | 3 | 2.7 | 0.3 | 3 |  | 17
19 | Construction of Land/ Drain from main road to h/o Swarn at village Kotla Trewa | Ongoing | Jammu | Arnia | Trewa | 1.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13.5
20 | Construction of Land/ Drain from h/o Satpal to h/o Yash Pal at village Kotla Trewa | Ongoing | Jammu | Arnia | Trewa | 1.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13.5
21 | Construction of Land/ Drain from Panchayat Ghar to Charan Dass | Ongoing | Jammu | Arnia | Changia | 1.5 | INFRA- I | 12 | 2018-19 | 2020-21 | 3 | 4.5 | 0.5 | 5 |  | 26.5
22 | Construction of Land/ Drainrain from h/o Babu Ram to Bachan Lal and allied links at Kirchpur | Ongoing | Jammu | Arnia | Kathar | 2 | INFRA- I | 5.25 | 2018-19 | 2019-20 | 3 | 2.02 | 0.225 | 2.245 |  | 14.74
23 | Repair/Renovation of Pond at village Allah-II | Ongoing | Jammu | Arnia | Allah | 2 | INFRA- I | 10 | 2018-19 | 2020-21 | 3 | 2.7 | 0.3 | 3 |  | 21
24 | Construction of road from main road marhole to onwards | Ongoing | Jammu | Arnia | Chak Majra | 5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 17
25 | Construction of platform at khurli at village Sohagpur | Ongoing | Jammu | Arnia | Pachail | 6 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 18
26 | Construction of road by laying of RBM from Nikki Payi to Biaspur Kalyana road at village Arnia | Ongoing | Jammu | Arnia | Arnia | 2 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.92 | 1.872 | 0.208 | 2.08 |  | 1431.8
27 | Imp and Extensioon of Water supply Village Kotla Jorian | Ongoing | Jammu | Arnia | Kotla Jorian | 3.5 | SOCIAL | 5 | 2017-18 | 2019-20 | 3.122 | 1.69 | 0.19 | 1.88 |  | 15.382
28 | Imp amd Extension of Water Suppy vllage Chak Shibu | Ongoing | Jammu | Arnia | Chak Shibu | 5 | SOCIAL | 5 | 2017-18 | 2019-20 | 2.54 | 2.214 | 0.246 | 2.46 |  | 17.46
29 | Imp./strengtheining of Electric System including upgradation of various pumping stations. | Ongoing | Jammu | Arnia | Kathar Changian Trewa Kaku De Kothey Shibu Chak | 3 | SOCIAL | 5 | 2017-18 | 2019-20 | 2.375 | 2.358 | 0.262 | 2.62 |  | 15.615
30 | Repair/Renovation of GHS Trewa | Ongoing | Jammu | Arnia | Trewa | 0-5 | EDUCATION | 5.2 | 2018-19 | 2019-20 | 2.5 | 2.43 | 0.27 | 2.7 |  | 13.1
31 | Balance work for Construction of a room with attached bathroom for female Patients (Antenatal Cases) at PHC Arnia (On going). | Ongoing | Jammu | Arnia | Arnia | 4 | HEALTH | 10 | 2018-19 | 2019-20 | 6.86 | 2.826 | 0.314 | 3.14 |  | 27.14
32 | Creation of 100 KVA S/Stn. at Jabowal and Mulla Chak alongwith HT & LT line and extension of LT line in Arnia Block | New | Jammu | Arnia | Laxmanpura & Mandal | 0-6 | SOCIAL | 12 | 2019-20 | 2019-20 | 0 | 10.8 | 1.2 | 12 |  | 36
33 | Construction of D/Channel at Chak Kirpal Pur Moh. Middle School | Ongoing | Jammu | Bhalwal Brahamana | Chak Kirpal Pur | 10 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 22
34 | Construction of Land/ Drain at Chack Biasa | Ongoing | Jammu | Bhalwal Brahamana | Chak Kirpal Pur | 10 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 22
35 | Construction of Tractor Roads at Jamotian Moh. Beena Walli | Ongoing | Jammu | Bhalwal Brahamana | Jamotian | 6 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 18
36 | Construction of Balance work of Link Road at Mawa w. no. 5 Anddo Nallah | Ongoing | Jammu | Bhalwal Brahamana | Mawa Brahmana | 6 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 18
37 | Construction of Link Road at Jadh Moh. Chowkidaar | Ongoing | Jammu | Bhalwal Brahamana | Jadh | 8 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 20
38 | Improvement of water supply to Malla Mohalla Jamotian under WSS Jamotian | Ongoing | Jammu | Bhalwal Brahamana | Jamotian | 10 | SOCIAL | 7 | 2017-18 | 2020-21 | 3.31 | 2.15 | 0.24 | 2.39 |  | 25.09
39 | Repair/Renovation of 2 rooms at PS Koudewala | Ongoing | Jammu | Bhalwal Brahamana | Bhalwal Brahmna | 0-5 | EDUCATION | 2 | 2018-19 | 2019-20 | 1 | 0.9 | 0.1 | 1 |  | 5
40 | Construction of B/Wall at PS Batla | Ongoing | Jammu | Bhalwal Brahamana | chak Kirpalpur | 0-5 | EDUCATION | 3.5 | 2018-19 | 2019-20 | 1.5 | 1.8 | 0.2 | 2 |  | 9
41 | Balance work for Construction of Boundary Wall and Main Gate at PHC Bhalwal Brahamna (On going). | Ongoing | Jammu | Bhalwal Brahamana | Bhalwal Brahamna | 7 | HEALTH | 6.8 | 2018-19 | 2020-21 | 2.84 | 1.8 | 0.2 | 2 |  | 20.64
42 | Construction of Solid Liquid Resource Managemnet shed (Swatch Bharat Mission) at near Pyt.Ghar Bhalwal. Brahmana | New | Jammu | Bhalwal Brahamana | Bwl. Brahmana | 3 | SOCIAL | 21 | 2019-20 | 2020-21 | 0 | 7.2 | 0.8 | 8 |  | 40
43 | Construction of road from link Chingia to Chanana (Byepass road) | Ongoing | Jammu | Bishnah | Chingia , Trewa, Chanana | 0.5 | INFRA- I | 60 | 2018-19 | 2020-21 | 17.32 | 13.86 | 1.54 | 15.4 |  | 108.62
44 | Repair/Restoration/improvement of the tube wells falling in Arnia Block | Ongoing | Jammu | Bishnah | Jajowal -II, Jajowal -III and Arnia A-II | 2 | SOCIAL | 6 | 2017-18 | 2019-20 | 4.01 | 1.791 | 0.199 | 1.99 |  | 15.99
45 | Improvement of Channel at tube well Nandpur, Arnia C and trewa | Ongoing | Jammu | Bishnah | Arnia | 4 | SOCIAL | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 16.5
46 | Approach road to Rehal stadium | New | Jammu | Bishnah | Rehal | 4 | INFRA- I | 15 | 2019-20 | 2020-21 | 0 | 8.48 | 0.94 | 9.42 |  | 37.84
47 | Construction of Lane & Drain & allied work Moh.Deep Raj and Moh. Roshan lal W.No 1 | Ongoing | Jammu | Kharah bali | Battal | 1.5 | INFRA- I | 6 | 2018-19 | 2019-20 | 2.5 | 3.15 | 0.35 | 3.5 |  | 17
48 | Constructionof Lane & allied work at Nabla to onward Mallah and upgradation of Link Road from Sansar to upper Pukharni. | Ongoing | Jammu | Kharah bali | Mallah | 3 | INFRA- I | 7 | 2018-19 | 2019-20 | 3 | 3.6 | 0.4 | 4 |  | 21
49 | Constructionof Well at Gajuban & Lane With P/work from Nallah to H/O Mulkh Raj | Ongoing | Jammu | Kharah bali | serh | 5 | SOCIAL | 5.5 | 2018-19 | 2019-20 | 2 | 3.15 | 0.35 | 3.5 |  | 19.5
50 | Const .of Lane/Drain with allied work at Village Mukeri Pyt.Battal | Ongoing | Jammu | Kharah bali | Battal | 1.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13.5
51 | Neeli Nallah Saryalla road at Malla Pukhrani road | Ongoing | Jammu | Khour | Neeli Nallah Saryalla Malla Pukhrani | 2 | INFRA- I | 155.4 | 2003-04 | 2021-22 | 77.44 | 5.6 | 0.62 | 6.22 |  | 247.28
52 | link road Sahib Bandagi Ashram to Nai Basti Naryana | Ongoing | Jammu | Khour | Nai Basti Naryana | 3 | INFRA- I | 44.68 | 2009-10 | 2019-20 | 38.94 | 5.16 | 0.58 | 5.74 |  | 98.1
53 | Link Road Mukeri to Razani | Ongoing | Jammu | Khour | Sumouh | 2 | INFRA- I | 130 | 2009-10 | 2021-22 | 80.34 | 9 | 1 | 10 |  | 232.34
54 | Link road to Shoara | Ongoing | Jammu | Khour | Shoara | 3 | INFRA- I | 86.2 | 2009-10 | 2020-21 | 55.36 | 9.73 | 1.08 | 10.81 |  | 166.18
55 | Construction of RCC HP Culvert on various roads in Chhamb Consty. | Ongoing | Jammu | Khour | Chhamb | 2 | INFRA- I | 80 | 2018-19 | 2021-22 | 10 | 9 | 1 | 10 |  | 112
56 | Construction of road from Sarwal to Fukwwari via Nabble Chak. | Ongoing | Jammu | Khour | Pargwal | 1 | INFRA- I | 75 | 2018-19 | 2021-22 | 10 | 6.3 | 0.7 | 7 |  | 100
57 | Construction of Community Hall at village Dardora | Ongoing | Jammu | Khour | Bakore | 6 | SOCIAL | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 18.5
58 | Augmentation of water supply in Dhakkar | Ongoing | Jammu | Khour | Dhakkar | 0-10 | SOCIAL | 15 | 2018-19 | 2019-20 | 1.471 | 12.177 | 1.353 | 13.53 |  | 43.531
59 | Construction of 01 no. Toilet Units at Govt. M.S Garar | Ongoing | Jammu | Khour | Sainth | 0-5 | EDUCATION | 2 | 2018-19 | 2019-20 | 0.8 | 1.08 | 0.12 | 1.2 |  | 5.2
60 | Construction of 01 no. Toilet Units at Govt. H.S Khour | Ongoing | Jammu | Khour | Naryana Lower | 0-5 | EDUCATION | 2 | 2018-19 | 2019-20 | 0.8 | 1.08 | 0.12 | 1.2 |  | 5.2
61 | Balance work for Construction/up gradation of SC Gigeriya (On going). | Ongoing | Jammu | Khour | Gigeriyal | 2 | HEALTH | 5 | 2018-19 | 2019-20 | 3.43 | 1.413 | 0.157 | 1.57 |  | 13.57
62 | Balance work for Renovation & Construction of Boundary Wall, Tiling of Toilets & sanitary fitting at Sub Centre Naryana (On going). | Ongoing | Jammu | Khour | Naryana | 4 | HEALTH | 9.48 | 2018-19 | 2019-20 | 3.44 | 5.436 | 0.604 | 6.04 |  | 29
63 | Construction of road from main road Sainth upto h/o Deep Raj at village Sainth, Block Khour | New | Jammu | Khour | Sainth | 2 | INFRA- I | 51 | 2019-20 | 2021-22 | 0 | 18 | 2 | 20 |  | 93
64 | Creation of 63 KVA S/Stn. at Indri, Garar and Gurah Manhansan alongwith HT & LT line | New | Jammu | Khour | Indri, Garar & Gurha Manashan | 0-6 | SOCIAL | 12 | 2019-20 | 2019-20 | 0 | 10.8 | 1.2 | 12 |  | 36
65 | Construction of road from Gossian Chak to Nowada Chak & Wazir Chak to Chak Desa Singh. | Ongoing | Jammu | Mandal Phalian | Chak Desa | 6 | INFRA- I | 60 | 2018-19 | 2021-22 | 8.9 | 13.25 | 1.47 | 14.72 |  | 104.34
66 | Imp./ Construction of road from Sure Chak to Sampuranpur Kullian | Ongoing | Jammu | Mandal Phalian | Kullian | 6 | INFRA- I | 50.35 | 2011-12 | 2020-21 | 25.36 | 6.3 | 0.7 | 7 |  | 95.71
67 | Balance work of Community Hall at village Alora | Ongoing | Jammu | Mandal Phalian | Sohanjana | 3 | SOCIAL | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 15
68 | Construction of lane/drain from main road to Jaggar Ram Land at Makwal | Ongoing | Jammu | Mandal Phalian | Makwal | 1.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13.5
69 | Construction of lane/drain at Murarpur | Ongoing | Jammu | Mandal Phalian | Makwal | 2 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 14
70 | Construction of lane/drain from H/o Mohan lal to h/o Kamal kumar at Alora | Ongoing | Jammu | Mandal Phalian | Sohanjana | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 15
71 | Construction of lane/nallah near land of Jagga Ram at Haripur | Ongoing | Jammu | Mandal Phalian | Haripur | 4 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 16
72 | Balance work of Community Hall at Malkey chak | Ongoing | Jammu | Mandal Phalian | Sum | 3.5 | SOCIAL | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 16
73 | Construction of Community Hall at Top manhasan | Ongoing | Jammu | Mandal Phalian | Sum | 3 | SOCIAL | 10 | 2018-19 | 2019-20 | 4 | 5.4 | 0.6 | 6 |  | 29
74 | Construction of lane/drain/p/wall near H/o Bunty kumar and Om parkash at Kirpalpur | Ongoing | Jammu | Mandal Phalian | Mandal | 6 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 18.5
75 | Construction of nallah/p/wall near land of Vimal Rakwal at Thalwal | Ongoing | Jammu | Mandal Phalian | Parladhpur | 4.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 17
76 | Balance work for Up gradation of CHC Sohanjana, demolition of old standing structure opposite residential quarters and construction of Doctors/staff car parking and up-gradation of residential quarters at CHC Sohanjana (On going). | Ongoing | Jammu | Mandal Phalian | Sohanjana | 4.5 | HEALTH | 9.4 | 2018-19 | 2019-20 | 6.44 | 2.664 | 0.296 | 2.96 |  | 26.26
77 | Up-gradation of road from Rakh Makwal to BSF Post | New | Jammu | Mandal Phalian | Makwal | 0.5 | INFRA- I | 60 | 2019-20 | 2021-22 | 0 | 18 | 2 | 20 |  | 100.5
78 | Construction of ladies bathroom at sum near panchayat ghar | New | Jammu | Mandal Phalian | Sum | 3 | SOCIAL | 5 | 2019-20 | 2019-20 | 0 | 4.5 | 0.5 | 5 |  | 18
79 | Internal road Gajansoo Bazar | Ongoing | Jammu | Marh | Gajansoo | 1.5 | INFRA- I | 25 | 2018-19 | 2020-21 | 6.85 | 4.5 | 0.5 | 5 |  | 43.35
80 | Internl road Rakh nagbani | Ongoing | Jammu | Marh | Gangu Parwah | 3 | INFRA- I | 35 | 2018-19 | 2020-21 | 5.48 | 4.5 | 0.5 | 5 |  | 53.48
81 | Main road Kullian to Salaria House upto Ashram. | Ongoing | Jammu | Marh | Halqa | 3 | INFRA- I | 35 | 2018-19 | 2020-21 | 5.48 | 3.6 | 0.4 | 4 |  | 51.48
82 | Internal link at village Bachyal. | Ongoing | Jammu | Marh | Chanu chak | 2.5 | INFRA- I | 30 | 2018-19 | 2020-21 | 4.8 | 4.5 | 0.5 | 5 |  | 47.3
83 | Link road to Simbli | Ongoing | Jammu | Marh | Jaswan | 2 | INFRA- I | 30 | 2018-19 | 2020-21 | 4.8 | 3.6 | 0.4 | 4 |  | 44.8
84 | Consrruction of road from Deora nappu to Boria Basti | Ongoing | Jammu | Marh | Boria Basti | 2 | INFRA- I | 25 | 2017-18 | 2020-21 | 12 | 7.06 | 0.79 | 7.85 |  | 54.7
85 | Construction of Community Hall at channi Mamalian | Ongoing | Jammu | Marh | Marh | 5 | SOCIAL | 5.5 | 2017-18 | 2019-20 | 1.11 | 3.951 | 0.439 | 4.39 |  | 20.39
86 | Construction of lane/drain Mohalla Prabhu Ram at Kanachak | Ongoing | Jammu | Marh | Kana chak | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 15
87 | Construction of lane at Kana chak village from Shiv Dev Singh to Rounak Singh lane | Ongoing | Jammu | Marh | Kana chak | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 15
88 | Black Topping of raod at Upper Bathore, Nai Bast. | Ongoing | Jammu | Marh | Nai Bast | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
89 | Black Topping of raod from main road to onwards at Nai Bast. | Ongoing | Jammu | Marh | Nai Bast | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
90 | Construction of lane/drain at Flora Haramkund Moh.2nd | Ongoing | Jammu | Marh | Dhateriyal | 5.5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 17.5
91 | Construction of lane at Mahavir Basti Sandwan | Ongoing | Jammu | Marh | Gho-Manahasan | 6 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 18
92 | Construction of lane at Kothey | Ongoing | Jammu | Marh | Sohagani | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 15
93 | Construction of lane/drain at Halqua Moh.SC near Tara Chand house | Ongoing | Jammu | Marh | Halqua | 6 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 18
94 | Construction of lane/drain at Smailpur Moh.SC | Ongoing | Jammu | Marh | Gangwah Parwah | 7 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 19
95 | Construction of lane/drain at Patyali Chak | Ongoing | Jammu | Marh | Sangrampur | 5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 17
96 | Construction of lane at Marh Bhag | Ongoing | Jammu | Marh | Marh | 5 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 17
97 | Construction of lane/drain near house of Jagger Chowhdhary and others at Karloop | Ongoing | Jammu | Marh | Karloop | 4 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 16.5
98 | Construction of lane at Plaserey | Ongoing | Jammu | Marh | Flora Nagbani | 7 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 19.5
99 | Installation of shallow hand pumps (Non Potable) | Ongoing | Jammu | Marh | Chak Dalli Jaswan Makwal Bhure Chak Nai Basti Gagansoo Sohanjana | 3 | SOCIAL | 5 | 2018-19 | 2019-20 | 3.9 | 0.99 | 0.11 | 1.1 |  | 14.1
100 | Repair/Renovation of 2 rooms & Construction Of 1 Addl. Classroom at PS Gole Pattan | Ongoing | Jammu | Marh | Gango Chak | 0-5 | EDUCATION | 6 | 2018-19 | 2019-20 | 2.5 | 3.15 | 0.35 | 3.5 |  | 15.5
101 | Repair/Renovation of 2 rooms & Construction Of 1 Addl. Classroom at MPS Gajansoo | Ongoing | Jammu | Marh | Gajansoo | 0-5 | EDUCATION | 6 | 2018-19 | 2019-20 | 2.5 | 3.15 | 0.35 | 3.5 |  | 15.5
102 | Balance work for Construction of additional room at SDH Marh (On going). | Ongoing | Jammu | Marh | Marh | 4 | HEALTH | 6.5 | 2018-19 | 2019-20 | 3.05 | 3.105 | 0.345 | 3.45 |  | 20.45
103 | Construction of P/work of road near chak dam at Burj Jaswan | New | Jammu | Marh | Jaswan | 5 | OTHER INFRA. | 10 | 2019-20 | 2019-20 | 0 | 9 | 1 | 10 |  | 35
104 | Construction of Computor Lab at BHQ Marh | New | Jammu | Marh | Marh | 6 | EDUCATION | 20 | 2019-20 | 2020-21 | 0 | 11.73 | 1.3 | 13.03 |  | 52.06
105 | Creation of 100 KVA S/Stn. at Chargali, Punnu-Di-Hatti and Layal (Gujjar Basti) alongwith HT & LT line | New | Jammu | Marh | Chargali, Punnu-Di-Hatti and Lalyal | 0-5 | SOCIAL | 12 | 2019-20 | 2019-20 | 0 | 10.8 | 1.2 | 12 |  | 36
106 | Construction of culvert near house of Madan at Marh kulley | Ongoing | Jammu | Pargwal | Pargwal upper | 4 | INFRA- I | 5 | 2018-19 | 2019-20 | 2 | 2.7 | 0.3 | 3 |  | 17
107 | Construction of drain from Mohalla kulley to Seam nallah | Ongoing | Jammu | Pargwal | Sarwal | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 2 | 2.7 | 0.3 | 3 |  | 16
108 | Construction of community shed near temple at village Pargwal | Ongoing | Jammu | Pargwal | Pargwal | 4 | SOCIAL | 10 | 2018-19 | 2020-21 | 3 | 2.7 | 0.3 | 3 |  | 23
109 | Construction of lane/drain at kanachak | Ongoing | Jammu | R.S Pura | Puro Bana | 4 | INFRA- I | 10 | 2018-19 | 2020-21 | 3 | 2.7 | 0.3 | 3 |  | 23
110 | Construction of lane/drain at langerial | Ongoing | Jammu | R.S Pura | Fatehpur Brahmana | 2 | INFRA- I | 10 | 2018-19 | 2020-21 | 3 | 2.7 | 0.3 | 3 |  | 21
111 | Construction of lane/drain at Badyal derian | Ongoing | Jammu | R.S Pura | Badyal Brahmana upper | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 2516.321
112 | Construction of lane/drain at Badyal Brahmana | Ongoing | Jammu | R.S Pura | Badyal Brahmana lower | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.68 | 2.088 | 0.232 | 2.32 |  | 15.32
113 | Construction of lane/drain at New Agra chak | Ongoing | Jammu | R.S Pura | Chak Agra | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 15
114 | Construction of lane/drain at kheper | Ongoing | Jammu | R.S Pura | Jassore | 4 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 30.32
115 | Laying of tiles near Sahib bandagi Community Hall at village kothey kalyana | Ongoing | Jammu | R.S Pura | Kalyana | 5 | INFRA- I | 8.8 | 2018-19 | 2020-21 | 2 | 2.26 | 0.25 | 2.51 |  | 20.82
116 | Construction of Community Hall at Badyal Brahmana | Ongoing | Jammu | R.S Pura | Badyal Brahmana | 3 | SOCIAL | 10 | 2018-19 | 2020-21 | 3 | 1.8 | 0.2 | 2 |  | 20
117 | Construction of balance work with fixing of tiles at Community Hall village and pyt. Kotli Galabana | Ongoing | Jammu | R.S Pura | Kotli Gala bana | 3 | SOCIAL | 10 | 2018-19 | 2020-21 | 3 | 2.7 | 0.3 | 3 |  | 40.82
118 | Installation of shallow hand pumps (Non Potable) | Ongoing | Jammu | R.S Pura | Kotli Shah Doula Baspur | 4 | SOCIAL | 8.65 | 2017-18 | 2019-20 | 2.64 | 5.41 | 0.6 | 6.01 |  | 27.31
119 | Repair/Restoration/improvement of the tube wells falling in R.S Pura Block | Ongoing | Jammu | R.S Pura | Ghora Bains, Bala Chak, Qutab Nizam, Simble Camp | 4 | SOCIAL | 8 | 2017-18 | 2019-20 | 6.46 | 1.386 | 0.154 | 1.54 |  | 21.54
120 | Development of Park at Bandowala near GREF Camp | Ongoing | Jammu | Samwan | Pallanwala Upper | 3 | AGRI | 7.5 | 2018-19 | 2020-21 | 2.6 | 1.8 | 0.2 | 2 |  | 17.1
121 | Construction of Community Hall at village Kala kass | Ongoing | Jammu | Samwan | Bardoh | 2 | SOCIAL | 7 | 2018-19 | 2019-20 | 2.6 | 3.96 | 0.44 | 4.4 |  | 20.4
122 | Construction Of 2 ACRs at GPS Khoi Millan | Ongoing | Jammu | Samwan | Samwan | 0-5 | EDUCATION | 8 | 2018-19 | 2019-20 | 3 | 4.5 | 0.5 | 5 |  | 21
123 | Improvement of Channel at Tube well Makwal I and Makwal II/III and fencing to Makwal Tube well I | Ongoing | Jammu | Satwari | Makawal-I/II/III | 2 | SOCIAL | 5 | 2018-19 | 2019-20 | 2.234 | 2.493 | 0.277 | 2.77 |  | 14.774
124 | Construction of Community Hall at Satrayian | Ongoing | Jammu | Suchetgarh | Satrayian | 2.5 | SOCIAL | 158 | 2011-12 | 2021-22 | 70.23 | 1.8 | 0.2 | 2 |  | 234.73
125 | Link road from Indira Menorial Academy Khanachak to Rangpur Mulana | Ongoing | Jammu | Suchetgarh | Khanachak | 6 | INFRA- I | 32 | 2017-18 | 2020-21 | 22.83 | 1.8 | 0.2 | 2 |  | 64.83
126 | Construction of Lane/ Drain at village Abdal | Ongoing | Jammu | Suchetgarh | Abdal | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
127 | Construction of lane/drain at village Khushalpur, Pyt. Abtal | Ongoing | Jammu | Suchetgarh | Abdal | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
128 | Construction Community Facility Center at Tibba Bhein | Ongoing | Jammu | Suchetgarh | Chak baja | 4 | SOCIAL | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 16
129 | Construction of 2 No.s Lane/ Drain at Tibba Bhein | Ongoing | Jammu | Suchetgarh |  | 3 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 15
130 | Construction of Lane/ Drain from house of puran chand to house of Des raj at chakroi | Ongoing | Jammu | Suchetgarh | Chakroi | 2 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 14
131 | Construction of 2 No.s Lane/ Drain at village Mana | Ongoing | Jammu | Suchetgarh | Dewangarh | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
132 | Construction of 2 No. Lane/ Drain near house of Manjeet singh and Balwant raj at village flora | Ongoing | Jammu | Suchetgarh | Flora | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
133 | Construction of Lane/ Drain at F.P Shekha (Mohalla Jatta) | Ongoing | Jammu | Suchetgarh |  | 1 | INFRA- I | 6 | 2018-19 | 2020-21 | 2.5 | 1.8 | 0.2 | 2 |  | 13.5
134 | Constt of drain at Gharani near gurudwara | Ongoing | Jammu | Suchetgarh | Gharana | 4 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 16
135 | Construction of Lane/ Drain house of Balak ram to onwards at Gharani | Ongoing | Jammu | Suchetgarh |  | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
136 | Construction of Lane/ Drain at Fathuchak | Ongoing | Jammu | Suchetgarh | Haripur | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
137 | Construction of Lane/ Drain from house of Jagdish Raj to link road at Haripur | Ongoing | Jammu | Suchetgarh |  | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
138 | Construction of compound wall and drain at bhojpur | Ongoing | Jammu | Suchetgarh | R.P Mullana | 1 | SOCIAL | 5 | 2018-19 | 2019-20 | 3 | 1.8 | 0.2 | 2 |  | 13
139 | Construction of 3 no. Land/ Drain at village Karotana Khurd | Ongoing | Jammu | Suchetgarh | Suchetgarh | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.94 | 1.86 | 0.2 | 2.06 |  | 13.06
140 | Construction of Lane/ Drain at Bidipur Jatta | Ongoing | Jammu | Suchetgarh | Bidipur Jatta | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 13.5
141 | Construction of Lane/ Drain near house of Pritam lal at village Nai basti | Ongoing | Jammu | Suchetgarh | Nai basti | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 13.5
142 | Construction Community Facility Center at suchetgrh | Ongoing | Jammu | Suchetgarh | suchetgrh | 1 | SOCIAL | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 13.5
143 | Construction of Lane/ Drain from gurudwara sahib to ownward at suchetgarh | Ongoing | Jammu | Suchetgarh | suchetgrh | 1 | INFRA- I | 5 | 2018-19 | 2019-20 | 2.5 | 2.25 | 0.25 | 2.5 |  | 13.5
144 | Construction of Lane/ Drain at village Panjgrain | Ongoing | Jammu | Suchetgarh | Talhar | 2 | INFRA- I | 10 | 2018-19 | 2020-21 | 3.17 | 1.24 | 0.14 | 1.38 |  | 17.93
145 | Installation of shallow hand pumps (Non Potable) | Ongoing | Jammu | Suchetgarh | Rangpur Sidhra Sai, G.S Pura D , Sai A-III Chakroi B | 5 | SOCIAL | 9.92 | 2018-19 | 2019-20 | 6.02 | 3.51 | 0.39 | 3.9 |  | 28.74
146 | Repair/renovation of Class rooms at HSS Sai Kalan | Ongoing | Jammu | Suchetgarh | Sai kalan | 0-5 | EDUCATION | 9 | 2018-19 | 2020-21 | 4 | 1.42 | 0.16 | 1.58 |  | 16.16
147 | Repair/renovation of Class rooms at GHSS Chakrohi | Ongoing | Jammu | Suchetgarh | Chakrohi | 0-5 | EDUCATION | 6 | 2018-19 | 2020-21 | 2.2 | 0.9 | 0.1 | 1 |  | 10.2
148 | Construction Of C/Wall of Govt. PS Paswalgarh | Ongoing | Jammu | Suchetgarh | Chakrohi | 0-5 | EDUCATION | 5.8 | 2018-19 | 2020-21 | 2.2 | 0.95 | 0.11 | 1.06 |  | 10.12
149 | Construction of Nallah from link road to onwards at Flora Pyt. Flora | New | Jammu | Suchetgarh | Sai Khurd | 1 | INFRA- I | 10 | 2019-20 | 2020-21 | 0 | 4.45 | 0.5 | 4.95 |  | 20.9
150 | Creation of 100 KVA S/Stn. at B. Brahamana and Gulab Garh Basti alongwith HT & LT and extension of LT line in Suchetgarh | New | Jammu | Suchetgarh | Border Villages | 0-7 | SOCIAL | 10.54 | 2019-20 | 2019-20 | 0 | 9.486 | 1.054 | 10.54 | `` | 31.62
151 | Construction of road from Gharani to Nawa Pind | New | Jammu | Suchetgarh | Gharani |  | INFRA- I | 20 | 2019-20 | 2020-21 | 0 | 9 | 1 | 10 |  | 40
| Total | [10 empty] | 560.239 | 62.256 | 622.495