## Kargil
Annual Action Plan (BADP) 2019-20 District Kargil (Rs. In lakhs)
S.No | Scheme/Works | Whether Scheme is New or On-going | District | Block | Village | Distance From LoC/ LAC | Sector | Estimated Cost | Years of Start | Target Year for completion of the scheme | Commul Exp incl USB 03/2019 | Allocation 2019-20
[12 empty] | Central Share | State Share | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Pony Track/foothpath from Gongma Thang to Yokma Thang batalik | ongoing | Kargil | Batalik | Silmo | 3 | INFRA-I | 50.75 | 2015-16 | 2020-21 | 19.71 | 4.5 | 0.5 | 5
2 | Extension of Link Road narabnee top Grong Silmo | ongoing | kargil | Batalik | Silmo | 3 | INFRA-I | 46.19 | 2016-17 | 2021-22 | 13.69 | 2.7 | 0.3 | 3
3 | Remodling of Irrigation canal at Lalung | ongoing | Kargil | Batalik | Lalung | 2 | AGRI | 51.5 | 2012-13 | 2019-20 | 30.82 | 18.61 | 2.07 | 20.68
4 | Construction Of Chortan at Garkone | on going | Kargil | Batalik | Garkone | 4 | OTHER INFRA | 15.38 | 2012-13 | 2019-20 | 11.44 | 3.55 | 0.39 | 3.94
5 | Construction of Link Road Spangstod Lalung | ongoing | Kargil | Batalik | Lalung | 2 | INFRA-I | 50 | 2015-16 | 2021-22 | 17.67 | 0.9 | 0.1 | 1
6 | Renovation/Repairing of Primary Health Center Batalik | ongoing | kargil | Batalik | Silmo | 3 | HEALTH | 50 | 2016-17 | 2021-22 | 6.19 | 2.7 | 0.3 | 3
7 | Construction Of Sub-Center Gargardo | ongoing | Kargil | Batalik | Garkone | 4 | HEALTH | 68.38 | 2016-17 | 2021-22 | 11.84 | 3.41 | 0.38 | 3.79
8 | Upgradation Of Link Road Zargar Mohalla Bhimbat | ongoing | Kargil | Bhimbat | Bhimbat | 2 | INFRA-I | 54.55 | 2015-16 | 2020-21 | 31.04 | 3.6 | 0.4 | 4
9 | Upgradation Of Link Road Shakthang Mohalla Bimbhat | ongoing | Kargil | Bhimbat | Bhimbat | 2 | INFRA-I | 68.77 | 2015-16 | 2021-22 | 23.85 | 3.6 | 0.4 | 4
10 | Upgradation of Link Road Chokiyal | ongoing | Kargil | Bhimbat | chokiyal | 9 | INFRA-I | 68.3 | 2016-17 | 2021-22 | 11.8 | 3.6 | 0.4 | 4
11 | Upgradation of Link Road Chaspang | ongoing | Kargil | Bhimbat | Throngos | 2 | INFRA-I | 52.12 | 2016-17 | 2021-22 | 7.84 | 3.6 | 0.4 | 4
12 | Const of Link Road Niril Lamochan | ongoing | Kargil | Bhimbat | Youlboo | 3 | INFRA-I | 56.14 | 2017-18 | 2021-22 | 7.19 | 7.2 | 0.8 | 8
13 | Completion of pipe irrigation scheme Dandalthang Drass | ongoing | Kargil | Bhimbat | Jasgond | 9 | AGRI | 59.32 | 2012-13 | 2020-21 | 39.6 | 3.6 | 0.4 | 4
14 | Improvement of Irrigation Canal/Khul Dandal | ongoing | Kargil | Bhimbat | Jasgond | 9 | AGRI | 45 | 2016-17 | 2020-21 | 17.87 | 6.3 | 0.7 | 7
15 | Construction Of Middle School Nigore Phase-1st | ongoing | Kargil | Bhimbat | Bhimbat | 2 | EDUCATION | 50.35 | 2012-13 | 2019-20 | 32.9 | 15.7 | 1.75 | 17.45
16 | Construction Of Middle School Gindiyal Drass | ongoing | Kargil | Bhimbat | Gindiyal | 2 | EDUCATION | 134.25 | 2012-13 | 2021-22 | 94.57 | 7.12 | 0.79 | 7.91
17 | Construction of Primary School Kharboo Phase-Ist | ongoing | Kargil | Bhimbat | kharboo | 5 | EDUCATION | 50 | 2016-17 | 2021-22 | 15.8 | 3.6 | 0.4 | 4
18 | Construction of Middle School Chokiyal | ongoing | Kargil | Bhimbat | Chokiyal | 9 | EDUCATION | 50 | 2016-17 | 2021-22 | 11.17 | 3.6 | 0.4 | 4
19 | Improvement/Upgradation of Link Road khan Mohalla Taisboo Rambirpora | 0ngoing | Kargil | Drass | Ranbir pora | 3 | INFRA-I | 81.84 | 2013-14 | 2021-22 | 50.86 | 8.39 | 0.93 | 9.32
20 | Construction Of Link Road pologround Goshan to lamar via Giringgo upto Marpocho road. | ongoing | Kargil | Drass | Goshan | 2 | INFRA-I | 58.8 | 2014-15 | 2021-22 | 27.31 | 3.6 | 0.4 | 4
21 | Construction Of Link Road Holiyal from Mushkoo road to Akhone mohala Holiyal | ongoing | Kargil | Drass | Mushkoo | 2 | INFRA-I | 51.32 | 2014-15 | 2021-22 | 23.45 | 3.6 | 0.4 | 4
22 | Construction Of drain/footpath at Drass headqtr. | ongoing | Kargil | Drass | Ranbir pora | 3 | OTHER INFRA | 59.94 | 2015-16 | 2021-22 | 25.08 | 3.6 | 0.4 | 4
23 | Renovation/Repair of Old Ice Hockey ground Goshan | ongoing | Kargil | Drass | Goshan | 2 | SPORTS | 45 | 2017-18 | 2021-22 | 12.98 | 4.5 | 0.5 | 5
24 | Improvement Of Braknak Irrigation Canal Goshan | ongoing | Kargil | Drass | Goshan | 2 | AGRI | 108 | 2004-05 | 2019-20 | 98.77 | 8.31 | 0.92 | 9.23
25 | Construction Of Link Road Minjee Gond Mazarthang | 0ngoing | Kargil | Kargil | Minjee | 10 | INFRA-I | 115 | 2012-13 | 2021-22 | 43.97 | 3.6 | 0.4 | 4
26 | Construction Of Toilets facilities for women at kargil town | ongoing | Kargil | Kargil | Kargil | 7 | SOCIAL | 22.57 | 2015-16 | 2020-21 | 7.39 | 8.37 | 0.93 | 9.3
27 | Construction of Link Road Fraka Freth-jing Batambis Choskore | ongoing | Kargil | Kargil | Choskore | 10 | INFRA-I | 64.72 | 2015-16 | 2021-22 | 19.04 | 4.5 | 0.5 | 5
28 | Construction of Link Road Yokma Nyakto Graveyard Shingkhan Mohalla | ongoing | kargil | kargil | baroo | 8 | INFRA-I | 17.64 | 2016-17 | 2019-20 | 10.6 | 6.33 | 0.71 | 7.04
29 | Constt. Of Reserviour Tank Mayur Khul Chainigund | ongoing | Kargil | Kargil | Chuliskambo | 3 | AGRI | 135.31 | 2014-15 | 2022-23 | 8.26 | 3.6 | 0.4 | 4
30 | Remodeling of Main Water Reservoir at baroo, gongma | ongoing | kargil | kargil | baroo | 8 | AGRI | 67.14 | 2015-16 | 2021-22 | 24.63 | 3.6 | 0.4 | 4
31 | Remodeling of Irrigation Khul Gongyur, Titichumik | ongoing | Kargil | Kargil | Baroo | 8 | AGRI | 53.14 | 2015-16 | 2021-22 | 23.61 | 2.7 | 0.3 | 3
32 | Construction/Remodeling Of Myur Khul, Archoo Choskore Phase-I | ongoing | Kargil | Kargil | Choskore | 10 | AGRI | 63.15 | 2015-16 | 2021-22 | 19.96 | 3.6 | 0.4 | 4
33 | Remodelling of Mayur Khul Gongkha Stikchey RD 0-700mtr Phase-I | ongoing | Kargil | Kargil | Choskore | 10 | AGRI | 49.16 | 2016-17 | 2021-22 | 12.93 | 2.7 | 0.3 | 3
34 | Installation of Hand pumps for Kargil Block | ongoing | Kargil | Kargil | Kargil | 7 | INFRA-II | 15 | 2019-20 | 2019-20 | 6.67 | 7.5 | 0.83 | 8.33
35 | Construction Of Sedimentation tank at HeadWork of Water Supply Scheme Kargil. | ongoing | Kargil | Kargil | kargil | 7 | INFRA-II | 51.59 | 2015-16 | 2019-20 | 49.4 | 1.97 | 0.22 | 2.19
36 | Construction Of Footpath Yokstarang Choskore. | on going | Kargil | Kargil | Choskore | 10 | INFRA-I | 10 | 2016-17 | 2019-20 | 8.37 | 1.47 | 0.16 | 1.63
37 | Construction of Shelter Shed for Goma Kargil, Yokchoks, Lankore, Pishu Kako Shilikchey | on going | Kargil | Kargil | Kargil | 7 | S/S SCHEME | 24.78 | 2016-17 | 2020-21 | 9.35 | 2.7 | 0.3 | 3
38 | Repair of water reserviour tank at Yokchoks Deythang | on going | Kargil | Kargil | Kargil | 7 | INFRA-II | 16.77 | 2016-17 | 2019-20 | 9.95 | 6.14 | 0.68 | 6.82
39 | Construction of Link Road Munwara Mohallah Yokma Shilikchey | on going | Kargil | Kargil | Kargil | 7 | INFRA-I | 15 | 2016-17 | 2020-21 | 4.65 | 4.5 | 0.5 | 5
40 | Upgradation of drainage system Chanchik | ongoing | Kargil | Kargil | Kargil | 7 | OTHER INFRA | 50 | 2015-16 | 2021-22 | 26.02 | 2.7 | 0.3 | 3
41 | Establishment of Skill Development Training centers in different trades Pashmina Spinning, Tailoring & Knitting in various villages within the block. | ongoing | Kargil | Kargil | Kargil | 7 | SOCIAL | 8 | 2019-20 | 2019-20 | 6 | 1.8 | 0.2 | 2
42 | Construction of toilets at District Hospital kargil | ongoing | Kargil | Kargil | Kargil | 7 | HEALTH | 26.62 | 2015-16 | 2020-21 | 15.36 | 2.7 | 0.3 | 3
43 | Construction of Link Road Chomortan Hagnis | ongoing | Kargil | Sh.Chiktan | hagnis | 7 | INFRA-I | 48 | 2016-17 | 2021-22 | 1.8 | 3.6 | 0.4 | 4
44 | Construction of Retaining wall / Link Road Badyadoo Shakar | ongoing | Kargil | Sh.Chiktan | Shakar | 6 | INFRA-I | 49.47 | 2016-17 | 2021-22 | 9.36 | 3.6 | 0.4 | 4
45 | Construction of Link Road to Bawakha Ningnoos Hagnis | ongoing | Kargil | Sh.Chiktan | Hagnis | 7 | INFRA-I | 43.74 | 2016-17 | 2021-22 | 16.44 | 3.6 | 0.4 | 4
46 | Construction of Link Road from Dangchas To Chaechar | ongoing | Kargil | Sh.Chiktan | Hagnis | 7 | INFRA-I | 50.93 | 2016-17 | 2021-22 | 8.35 | 4.5 | 0.5 | 5
47 | Construction of Archery/Playfield at Hagnis | ongoing | Kargil | Sh.Chiktan | Hagnis | 7 | SPORTS | 28.85 | 2016-17 | 2020-21 | 6.33 | 3.6 | 0.4 | 4
48 | Constt of Jerzet Khul | ongoing | Kargil | Sh.Chiktan | Shakar | 6 | AGRI | 58.94 | 2016-17 | 2021-22 | 4.33 | 5.28 | 0.58 | 5.86
49 | Constt of Irrigation Khul Gangshan Shakar | ongoing | Kargil | Sh.Chiktan | Shakar | 6 | AGRI | 15 | 2017-18 | 2020-21 | 0 | 3.6 | 0.4 | 4
50 | Construction Of Oli Farkha Siachen Khul Samrah | ongoing | Kargi | Sh.Chiktan | Samrah | 9 | AGRI | 45.62 | 2014-15 | 2019-20 | 41.45 | 3.75 | 0.42 | 4.17
51 | Construction Of Khul Zbernaq at Shakar Rong | ongoing | Kargi | Sh.Chiktan | Shakar | 6 | AGRI | 10.19 | 2014-15 | 2019-20 | 10.11 | 0.07 | 0.01 | 0.08
52 | Construction of Reserviour Tank for irrigation at Yokma-Kharboo | ongoing | Kargil | Sh.Chiktan | Y-Kharbu | 5 | AGRI | 8.49 | 2016-17 | 2019-20 | 8.4 | 0.08 | 0.01 | 0.09
53 | Remodelling of Takmatan main khul at Hagnis | ongoing | Kargil | Sh.Chiktan | Hagnis | 7 | AGRI | 29.25 | 2016-17 | 2020-21 | 8.24 | 5.01 | 0.56 | 5.57
54 | Remodelling of Main Khul Kukshow | ongoing | Kargil | Sh.Chiktan | kushow | 7 | AGRI | 14.78 | 2016-17 | 2019-20 | 7.65 | 6.42 | 0.71 | 7.13
55 | Repair of reserviour tank at Dargoo | ongoing | Kargil | Sh.Chiktan | kushow | 7 | AGRI | 19 | 2016-17 | 2020-21 | 3.35 | 3.6 | 0.4 | 4
56 | Construction Of Link Road Chumorik Barchay | ongoing | Kargil | Sodh | Barchay | 4 | INFRA-I | 60 | 2009-10 | 2019-20 | 54.75 | 4.73 | 0.52 | 5.25
57 | Construction/ Upgradation of Link Road Rong Akchamal | ongoing | Kargil | Sodh | Akchamal | 3 | INFRA-I | 90 | 2014-15 | 2021-22 | 24.82 | 3.6 | 0.4 | 4
58 | Construction of Link Road Rzingboo to Zgnagchey Apati (Phase-I) | ongoing | Kargil | Sodh | Apati | 3 | INFRA-I | 60.49 | 2015-16 | 2021-22 | 24.48 | 4.29 | 0.48 | 4.77
59 | Construction/Improvement of Link Road Yourbaltak Fikar RD 0-1660 mtrs | ongoing | Kargil | Sodh | Yourbaltak | 3 | INFRA-I | 169.81 | 2015-16 | 2022-23 | 27.35 | 3.6 | 0.4 | 4
60 | Construction of Link Road Sharbatgrong to Biama Yourbaltak | ongoing | kargil | Sodh | Yourbaltak | 3 | INFRA-I | 51.54 | 2016-17 | 2021-22 | 18.36 | 3.6 | 0.4 | 4
61 | Construction Of Headwork Khul Mangbore Akchamal | ongoing | Kargil | Sodh | Akchamal | 3 | AGRI | 75 | 2012-13 | 2021-22 | 41.99 | 2.7 | 0.3 | 3
62 | Construction of Middle School Barchay | ongoing | Kargil | Sodh | barchay | 4 | EDUCATION | 53.37 | 2013-14 | 2020-21 | 43.25 | 1.8 | 0.2 | 2
| Grand Total | [10 empty] | 271.4 | 30.15 | 301.55
Note on D39: 3.67 Reduced 1.25: Const of Link Road Yokma (9) 0.83: Const Footpath Yokstarang Choskore (22) 1.59: Constt. Of Reserviour Tank Mayur Khul Chainigund (14)