## Kathua
Annual Action Plan for the year 2019-20 under Border Area Development Programme (District Kathua) (Rs in lakhs)
Sr. No. | Name of the work/project/scheme | Project Type (New/On-going) | District | Block | Village | Distance from IB/LOC (Kms) | Sector | Estimated cost | Year of comencement | Target for completion | Cum Expdt. incl USB 3/2019 | Allocation 2019-20
[12 empty] | Central Share | State Share | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Const of road from Sanji More to Korepunnu to SC ST Basti (Length = 1.80 Km) | ongoing | Kathua | Barnoti | Sanji More, Korepunnu | 5 | INFRA- I | 56.5 | 2013-14 | 2020-21 | 33.32 | 2.25 | 0.25 | 2.5
2 | Const of road from Sumwan Mohalla SC Basti and Gujjar Basti Via Kissan Nagar Mai Chak (Length = 2.00 Kms) | ongoing | Kathua | Barnoti | Sumwan/Mai Chak | 10 | INFRA- I | 72 | 2014-15 | 2020-21 | 42.21 | 4.5 | 0.5 | 5
3 | Constof road from link road Toda Chack to Jajli via Bakshi Jhumber | ongoing | Kathua | Barnoti | Toda Chack, Jajli. | 4 | INFRA- I | 41 | 2015-16 | 2020-21 | 11.01 | 2.93 | 0.32 | 3.25
4 | Imp./Upgradation of Mukandpur to Toda Chak road | ongoing | Kathua | Barnoti | Mukandpur, Toda Chak | 6 | INFRA- I | 43.7 | 2015-16 | 2020-21 | 11.68 | 2.25 | 0.25 | 2.5
5 | Const of link road from Khanpur to Palai (L = 2.00 Kms) | ongoing | Kathua | Barnoti | Palai | 7 | INFRA- I | 45 | 2016-17 | 2020-21 | 4.07 | 3.15 | 0.35 | 3.5
6 | Const of road from Karandi More to SC/ST Basti and Ext. upto village Muthi (L = 2 Kms) | ongoing | Kathua | Barnoti | Karandi, Muthi | 10 | INFRA- I | 70 | 2016-17 | 2021-22 | 5.51 | 0.9 | 0.1 | 1
7 | Const of road from Korepunnu to Partyal and Mehra | ongoing | Kathua | Barnoti | Partyal, Merhra | 5 | INFRA- I | 19.5 | 2016-17 | 2020-21 | 4.07 | 3.15 | 0.35 | 3.5
8 | Const of road from Jaymall Chak to house of Harnam Singh Haria Chak (L = 0.50 Km) | ongoing | Kathua | Barnoti | Jaymall Chak, Haria Chak | 5 | INFRA- I | 21.45 | 2016-17 | 2020-21 | 6.17 | 3.15 | 0.35 | 3.5
9 | Const of Maste Chak to Khanwal via Lower Khanwall road (L = 1.50 Km) | ongoing | Kathua | Barnoti | Maste Chak, Khanwal | 6 | INFRA- I | 50 | 2016-17 | 2021-22 | 5.5 | 0.9 | 0.1 | 1
10 | Construction of 02 culverts and Black Topping of Village Panchyat Road from link road Parkhwal to Ghair | ongoing | Kathua | Barnoti | Parkhwal, Ghair | 9 | INFRA- I | 50 | 2016-17 | 2021-22 | 7.83 | 0.9 | 0.1 | 1
11 | Black Topping of road from Khanak to Bobiya via Ladwal and Khanak Sapalwan road | ongoing | Kathua | Barnoti | Khanak, Bobiya, Ladwal, Sapalwan | 0 | INFRA- I | 25.75 | 2016-17 | 2020-21 | 8.9 | 4.81 | 0.55 | 5.36
12 | Upgradation of Dolia jatan Sotra Chak road (L=1.50 Km) | ongoing | Kathua | Barnoti | Dolia jatan Sotra Chak | 6 | INFRA- I | 44.3 | 2017-18 | 2021-22 | 8.73 | 1.72 | 0.19 | 1.91
13 | Const of road from OSK road to Bandhore (L= 1.15 Km) | ongoing | Kathua | Barnoti | Bandhore | 6 | INFRA- I | 48.9 | 2017-18 | 2021-22 | 9.17 | 3.15 | 0.35 | 3.5
14 | Const of road from Sultanpur to Andheychak to Labju Chak via Parnow (L = 3.00 Kms) | ongoing | Kathua | Barnoti | Sultanpur, Andheychak, Labju Chak, Parnow | 4 | INFRA- I | 30 | 2017-18 | 2020-21 | 2.67 | 1.8 | 0.2 | 2
15 | Construction of road from Sharma Rice Mill to SC Mohalla Khanpur | ongoing | Kathua | Barnoti | Khanpur | 7 | INFRA- I | 25 | 2018-19 | 2020-21 | 1 | 2.7 | 0.3 | 3
16 | Augmentation/Imp. Of water Supply scheme Haripur Sainia | ongoing | Kathua | Barnoti | Haripur Sainia | 4 | INFRA- II | 74.69 | 2011-12 | 2021-22 | 35.17 | 0.9 | 0.1 | 1
17 | Commissioing of New T/well Sumwan | ongoing | Kathua | Barnoti | Sumwan | 10 | INFRA- II | 87.75 | 2013-14 | 2020-21 | 53.6 | 3.9 | 0.43 | 4.33
18 | Imp. & Aug. of Water Supply Scheme Chak Sardar Attar Singh | ongoing | Kathua | Barnoti | Maida, Paharpur, Mehrajpur, Chhan Lal Din | 0 | INFRA- II | 68.1 | 2015-16 | 2021-22 | 12.89 | 0.9 | 0.1 | 1
19 | Imp. & Augmentation of water supply to village Pandori and Barmori. | ongoing | Kathua | Barnoti | Pandori, Barmori | 7 | INFRA- II | 35 | 2016-17 | 2020-21 | 14.57 | 2.7 | 0.3 | 3
20 | Water Supply Scheme Padyari | ongoing | Kathua | Barnoti | Padyari | 10 | INFRA- II | 122.12 | 2017-18 | 2022-23 | 6.77 | 0.9 | 0.1 | 1
21 | Creation of 100 KVA Sub Station at Banyari HT Line = 0.30 Km, LT Line = 0.20 Km & Augmentation of S/Stn 100 to 250 KVA at Padyari near D/9 canal | ongoing | Kathua | Barnoti | Banyari/Padyari | 5 | SOCIAL | 7.13 | 2018-19 | 2019-20 | 4.3 | 2.55 | 0.28 | 2.83
22 | Imp. Of Dhamni Khul | ongoing | Kathua | Barnoti | Pandyal/Barmori/ Pandori | 9 | AGRI | 27.6 | 2011-12 | 2019-20 | 22.58 | 4.52 | 0.5 | 5.02
23 | Imp. Of Chhan Lal Din No. I & II | ongoing | Kathua | Barnoti | Chhan Lal Din | 0 | AGRI | 12.4 | 2015-16 | 2019-20 | 10.86 | 1.41 | 0.13 | 1.54
24 | Imp. of Bagh Wali Khul | ongoing | Kathua | Barnoti | Salalpur | 6 | AGRI | 12 | 2016-17 | 2020-21 | 2.65 | 1.08 | 0.12 | 1.2
25 | Imp. Of Sarpail Pain Khul near the house of Sh Sain Din | ongoing | Kathua | Barnoti | Sarpail Pain | 4 | AGRI | 11.5 | 2017-18 | 2020-21 | 2.47 | 1.35 | 0.15 | 1.5
26 | Imp. Of Dragmal Khul | ongoing | Kathua | Barnoti | Tarafpain | 10 | AGRI | 24 | 2017-18 | 2020-21 | 2.8 | 0.72 | 0.08 | 0.8
27 | Imp. Of Malli Wali Khul | ongoing | Kathua | Barnoti | Bigwan | 10 | AGRI | 21 | 2017-18 | 2020-21 | 1.43 | 0.72 | 0.08 | 0.8
28 | Construction of road by way of MT & BT from OSK road to the new Panchyat Ghar, Marheen. | Ongoing | Kathua | Barnoti | Marheen | 6 | INFRA- I | 8 | 2018-19 | 2019-20 | 5.13 | 2.58 | 0.29 | 2.87
29 | Construction of irrigation embankments/minor irrigation works in villages Chann Lal Din, Kundey Chack, Mehrajpur | Ongoing | Kathua | Barnoti | Chann Lal Din, Kundey Chack, Mehrajpur | 5 | AGRI | 7 | 2018-19 | 2019-20 | 4.72 | 2.05 | 0.23 | 2.28
30 | Creation of 63 KVA SStn at Mandala, HT line = 0.20 Km, LT = 0.50 Km alongwith shifting of HT/LT line at Saidpur | New | Kathua | Barnoti | Mandala | 2 | SOCIAL | 10 | 2019-20 | 2019-20 | 0 | 8.69 | 0.98 | 9.67
31 | Widening of road from Hiranagar More to Hiranagar (L = 3.50 Kms) | ongoing | Kathua | Hiranagar | Hiranagar | 5 | INFRA- I | 150 | 2010-11 | 2020-21 | 130.92 | 1.8 | 0.2 | 2
32 | Const of road from Chakra to Chhan Tanda (L = 3.50 Km) | ongoing | Kathua | Hiranagar | Chakra, Chhan Tanda | 5 | INFRA- I | 92 | 2013-14 | 2021-22 | 55.34 | 2.7 | 0.3 | 3
33 | Imp/Upgradation of Chapaki link road & its links (Length = 6.30 Kms) | ongoing | Kathua | Hiranagar | Chapaki | 7 | INFRA- I | 146 | 2014-15 | 2022-23 | 41.58 | 2.7 | 0.3 | 3
34 | Const of road from Manyari Bobiya road to BOP Kotha post & BSF Post (L = 2.50 Kms) | ongoing | Kathua | Hiranagar | Manyari, Bobiya | 0 | INFRA- I | 62 | 2015-16 | 2021-22 | 17.25 | 2.7 | 0.3 | 3
35 | Const of road from Paharpur to village Mada (L =1 Km) | ongoing | Kathua | Hiranagar | Paharpur, Mada | 0 | INFRA- I | 39.7 | 2015-16 | 2021-22 | 13.15 | 2.7 | 0.3 | 3
36 | Improvement/Upgradation of Manyari Bobiya road (L = 7.00 Kms) | ongoing | Kathua | Hiranagar | Manyari, Bobiya | 0 | INFRA- I | 98 | 2016-17 | 2022-23 | 20.4 | 2.7 | 0.3 | 3
37 | Improvement/Upgradation of Sherpur and adjoining links (L = 1.50 Km) | ongoing | Kathua | Hiranagar | Sherpur | 3 | INFRA- I | 35 | 2016-17 | 2021-22 | 3.67 | 2.7 | 0.3 | 3
38 | Improvement/Upgradation of Sanyal link road (L = 3.40 Kms) | ongoing | Kathua | Hiranagar | Sanyal | 3 | INFRA- I | 163 | 2016-17 | 2022-23 | 4.67 | 1.35 | 0.15 | 1.5
39 | Const of Jandi to Jalla Chak road (L = 0.80 Km) | ongoing | Kathua | Hiranagar | Jandi, Jalla Chak | 5 | INFRA- I | 66.35 | 2016-17 | 2021-22 | 3.5 | 0.9 | 0.1 | 1
40 | Const of Jawhar Chak to Devo Chak road (L = 0.80 Km) | ongoing | Kathua | Hiranagar | Jawhar Chak Devo Chak | 3 | INFRA- I | 17.5 | 2016-17 | 2019-20 | 8.75 | 7.88 | 0.87 | 8.75
41 | Const of road from Chann Lal Din to Pansar (L = 2.40 Kms) | ongoing | Kathua | Hiranagar | Chann Lal Din, Pansar | 0 | INFRA- I | 119.35 | 2017-18 | 2022-23 | 3.77 | 2.7 | 0.3 | 3
42 | Const of road from Londi Kattal road to Dunga (L = 1.00 Km) | ongoing | Kathua | Hiranagar | Londi Kattal, Dunga | 0 | INFRA- I | 70.8 | 2017-18 | 2021-22 | 6.1 | 3.15 | 0.35 | 3.5
43 | Const of road from Jandi Kattal to Bassi (L=1.50 Km) | ongoing | Kathua | Hiranagar | Jandi Kattal, Bassi | 5 | INFRA- I | 63.25 | 2017-18 | 2021-22 | 1.67 | 3.15 | 0.35 | 3.5
44 | Imp. & Augmentation of water supply Scheme Muthi Charu | ongoing | Kathua | Hiranagar | Muthi Charu | 0 | INFRA- II | 46.9 | 2015-16 | 2020-21 | 20.76 | 3.37 | 0.37 | 3.74
45 | Water Supply Scheme Sube Chak | ongoing | Kathua | Hiranagar | Sube Chak | 6 | INFRA- II | 25 | 2017-18 | 2019-20 | 21.53 | 3.12 | 0.35 | 3.47
46 | Const of road by way of earth filling at village Gialwand to Manyari, Pyt Devochack | ongoing | Kathua | Hiranagar | Gialwand, Manyari | 0 | Rural Dev. | 20 | 2016-17 | 2019-20 | 18.73 | 1.14 | 0.13 | 1.27
47 | Const of play field ground at Jandi, Pyt Jandi | ongoing | Kathua | Hiranagar | Jandi | 5 | Rural Dev. | 25 | 2016-17 | 2019-20 | 20.804 | 3.78 | 0.42 | 4.2
48 | Const of 100 KVA Sub Station at Hore near Peer Baba, HT line = 0.30 km, LT = 0.30 km & Augmentation of S/stn 100 to 250 KVA at Haripur Pattle | ongoing | Kathua | Hiranagar | Hore, Haripur Pattle | 4 | SOCIAL | 7.2 | 2018-19 | 2019-20 | 4.42 | 2.5 | 0.28 | 2.78
49 | Imp. of Sherpur Nad Khul | ongoing | Kathua | Hiranagar | Sherpur Nad | 3 | AGRI | 12 | 2016-17 | 2019-20 | 5.98 | 5.42 | 0.6 | 6.02
50 | Imp. of Haripur Saini Khul | ongoing | Kathua | Hiranagar | Haripur Saini | 4 | AGRI | 12 | 2016-17 | 2019-20 | 6.34 | 5.09 | 0.57 | 5.66
51 | Improvement of Allu Chack Khul | ongoing | Kathua | Hiranagar | Allu Chak | 3 | AGRI | 24 | 2018-19 | 2021-22 | 0.54 | 0.54 | 0.06 | 0.6
52 | Improvement of Andhey Chack Khul | ongoing | Kathua | Hiranagar | Andhey Chack | 3 | AGRI | 22 | 2018-19 | 2021-22 | 0.54 | 1.43 | 0.16 | 1.59
53 | Improvement of Sherpur Khul | ongoing | Kathua | Hiranagar | Sherpur | 6 | AGRI | 25 | 2018-19 | 2021-22 | 1 | 0.9 | 0.1 | 1
54 | Laying of distribution system to mini Pansar from Tube well Nan Chak | New | Kathua | Hiranagar | Pansar | 0 | INFRA- II | 15.46 | 2019-20 | 2020-21 | 0 | 7.16 | 0.79 | 7.95
55 | Construction of Saidpur link road and link road to Bamyal road viz Bazoo (L = 6.00 Kms). | ongoing | Kathua | Kathua | Saidpur, Bazoo | 7 | INFRA- I | 305 | 2015-16 | 2022-23 | 123.92 | 9 | 1 | 10
56 | Const of link road from village Mirpur Ram to Nakkian Road (L = 2.00 Kms) | ongoing | Kathua | Kathua | Mirpur Ram, Nakkian | 8 | INFRA- I | 155 | 2016-17 | 2022-23 | 34.78 | 4.5 | 0.5 | 5
57 | Const of link road from village Goond to Shamshan ghat (L = 1.00 Km) | ongoing | Kathua | Kathua | Goond | 9 | INFRA- I | 41 | 2016-17 | 2021-22 | 7.75 | 9.55 | 1.06 | 10.61
58 | Const of 20 mtr long vented causeway Bajoo Nallah road Nagri to Shamshanghat | ongoing | Kathua | Kathua | Bajoo | 10 | INFRA- I | 108.66 | 2017-18 | 2021-22 | 51.42 | 11.7 | 1.3 | 13
59 | Augmentation of 3 Nos S/Stns at Pamwal, Jarai W. No. 4 and Badala W. No. 2 (100 KVA to 250 KVA each) and creation of 100 KVA Sub Station at Jakhbar, LT Line = 0.50 km | ongoing | Kathua | Kathua | Pamwal, Jarai, Badala, Jakhbar | 9 | SOCIAL | 13 | 2018-19 | 2019-20 | 8.8 | 3.78 | 0.42 | 4.2
60 | Augmentation of 100 to 250 KVA SStn at Lakhnote Check Post Nagri, Khokhyal & Goond | ongoing | Kathua | Kathua | Goondh | 9 | SOCIAL | 12.1 | 2019-20 | 2019-20 | 0 | 10.89 | 1.21 | 12.1
61 | Imp. Of Rumbli Wali Khul | ongoing | Kathua | Kathua | Khokhyal | 10 | AGRI | 20 | 2017-18 | 2020-21 | 2.63 | 0.87 | 0.1 | 0.97
62 | Imp. Of Patti Wali Khul | ongoing | Kathua | Kathua | Badala | 10 | AGRI | 21 | 2017-18 | 2020-21 | 3.3 | 2.25 | 0.25 | 2.5
63 | Improvement of Andhri Khul | ongoing | Kathua | Kathua | Saidpur | 7 | AGRI | 35 | 2018-19 | 2021-22 | 1 | 2.25 | 0.25 | 2.5
64 | Augmentation of sub station 100-250 KVA at Nangal & creation of 2 No. sub stations of 100 KVA at Goond More & Pamwal with HT = 0.50 Km & LT 0.70 Km Block Kathua | New | Kathua | Kathua | Nangal, Goond More & Pamwal | 8 | SOCIAL | 15.03 | 2019-20 | 2020-21 | 0 | 6.09 | 0.68 | 6.77
| Grand Total | [10 empty] | 205.69 | 22.85 | 228.54