## PHE & IFC
ANNUAL ACTION PLAN FOR THE YEAR 2019-20 UNDER BORDER AREA DEVELOPMENT PROGRAMME (PHE & I&FC DEPARTMENT) Rs. in lakhs
S.No. | Name of the Sector/Scheme | Project type ( New/On-going) | District | Block | Village | Arial Distance from IB/ LOC (KM) | Sector | Estd. Cost | Year of commencement (MM/YYYY) | Target completion (MM/YYYY) | Cum expdt incl USB 3/2019 | Allocation 2019-20
[12 empty] | C.S | S.S | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Imp/extension of WSS Amb Khori | On-going | Rajouri | Beri Pattan | Amb Khori | 8 KM | INFRA-II | 98.37 | 2017-18 | 2022-23 | 41.41 | 51.26 | 5.7 | 56.96
2 | Water Supply Scheme Hadipora | Ongoing | Baramulla | Rohama | Hadipora | 8 | INFRA-II | 411.62 | 2017-18 | 2020-21 | 152.5 | 131.41 | 14.6 | 146.01
3 | Upgradation/ Improvement of electro-mechanical equipment installed at Kukerian, Suhagni, Rathua, Rattanpur, Paras, Manval, Brahmana | Ongoing | Jammu | RS Pura / Bishna / Suchetghar | Talhar, Dewangarh, Chak Jandrian, Rakh Badyakl, Karotana, Bulla Chak, Lalupur Aajpur, Jabowal, Nikowal, Tagowali, G.S. Pura Rangpur Trewa | 5 | AGRI | 155.1 | 2017-18 | 2020-21 | 58.03 | 87.37 | 9.7 | 97.07
4 | Improvement/Upgradation of existing LIS Biaspur Parlah, Nikowal (New) & Pindi Sarochan (L/S of Gorore Nallah) (District Jammu). | Ongoing | Jammu | Marh | Kukerian, Suhagani, Rattan Pur Paras, Manyal Brahmana | 3.5 | AGRI | 70.55 | 2017-18 | 2020-21 | 50.55 | 18 | 2 | 20
5 | Improvement of channels and other allied works at Lift Irrigation Schemes Sai Kalan, Burajal & Nikowal (Jammu District). | Ongoing | Jammu | Sucheet Ghar | BiasPur Parlah, Nikowal (New) and Pindi Sarochan | 5 | AGRI | 95.49 | 2017-18 | 2020-21 | 45 | 45.44 | 5.05 | 50.49
6 | Drilling, Development & Commissioning of 06 number new Irrigation Tube-well in Akhnoor Tehsil of Jammu District. | Ongoing | Jammu | Sucheet Ghar | Sai Kallan, Burajal & Nikowal. | 1.5 | AGRI | 728.7 | 2017-18 | 2020-21 | 33.33 | 12.68 | 1.41 | 14.09
7 | Drilling Development & Commissioning of 05 number new Irrigation Tube-well in Suchetgarh Constituency of Jammu Distirct. | Ongoing | Jammu | Chamb / Akhnoor | Narayana, Jaz, Bag, Truti, Garh Saith and Mandi wala | 5 | AGRI | 679 | 2017-18 | 2020-21 | 33.33 | 11.15 | 1.24 | 12.39
8 | Improvement & Up-gradition of Tawi Lift Canal and its distribution system including Electro Mechanical Component Phase-II | Ongoing | Samba | Vijaypur & Ramgarh | Sarwa, Chak Doulat, Dabuj Kaka, Dabuj Shahzadpur, Gho Brahmana, Shahzadpur,Rari, Rara, Raika Labana, Raika Mehooba, Gho Rakwalan | 9 | AGRI | 747.49 | 2016-17 | 2021-22 | 216.14 | 104.54 | 11.62 | 116.16
| Grand Total | [10 empty] | 461.85 | 51.32 | 513.17