## Poonch
ANNUAL ACTION PLAN FOR THE YEAR 2019-20 UNDER BORDER AREA DEVELOPMENT PROGRAMME POONCH (Rs. In lakhs)
Sr.No. | Name of the project/ work/ scheme | Protect Type (New/ Ongoing) | District | Block | Village | Distance from IB/LOC (Kms) | Sector | Estd. cost | Year of Commencememnt | Target for completion | Cum. Expdtt. incl USB 3/2019 | Allocation 2019-20
[12 empty] | Central Share | State Share | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Const. of road from Saran Pati (Galutha) to Ari Patrara. 4 Kms | Ongoing | Poonch | Balakote | Saran Pati | 3.5 | INFRA -I | 196 | 2011-12 | 2021-22 | 30.16 | 4.45 | 0.49 | 4.94
2 | Link road Panaha Sudana Kotan to Panakhan | Ongoing | Poonch | Balakote | Sudana, Mustafa Nagar | 2 | INFRA -I | 76 | 2011-12 | 2021-22 | 24.84 | 0.9 | 0.1 | 1
3 | Const. of Water Harvesting Tanks | Ongoing | Poonch | Balakote | JW Gali, Upper Manjhari, Lower Manjhari, Kallar Morha, Bhata Dhurian, Nar, Sanjiote Upper, Sanjiote Lower, Dhargloon, Dharati, Bharoti | 0-10 | AGRI | 12 | 2019-20 | 2019-20 | 5.44 | 5.9 | 0.66 | 6.56
4 | Plants Planted/ Fencing on Govt./State Land | Ongoing | Poonch | Balakote | Dobi Dharati | 0-5 Km | AGRI | 5 | 2018-19 | 2019-20 | 2.04 | 2.66 | 0.3 | 2.96
5 | Plants Planted, Fencing, Pit Plantation, DRSM, Sowing, Maintt., Raising | Ongoing | Poonch | Balakote | Chajjla, Dharana, Tainwali, Ramkund & Balno | 0-5 Km | AGRI | 10 | 2018-19 | 2019-20 | 2.72 | 6.55 | 0.73 | 7.28
6 | Providing water facility to Mohra Jaba Manjhari | Ongoing | Poonch | Balakote | Jaba Manjhari | 2 Kms | INFRA-II | 94 | 2017-18 | 2021-22 | 17.8 | 1.8 | 0.2 | 2
7 | Const. of road from Tota Gali to Nakka. 6 Kms 4th to 6th | Ongoing | Poonch | Balakote | Totagali Nakka | 3 | INFRA -I | 165.67 | 2005-06 | 2021-22 | 38.14 | 4.5 | 0.5 | 5
8 | Const. of road from Naka to Nar | Ongoing | Poonch | Balakote | Nakka Nar | 3 | INFRA -I | 143.7 | 2010-11 | 2021-22 | 9.96 | 4.5 | 0.5 | 5
9 | Const. of road from 120 Infantry Brigade to Mendhar. L=2.80 Kms. 3rd | Ongoing | Poonch | Balakote | 120 Inf. Brigade | 2.5 | INFRA -I | 99.6 | 2009-10 | 2021-22 | 38.93 | 2.7 | 0.3 | 3
10 | Const. of road from main road to Dhargaloon road to Khet | Ongoing | Poonch | Balakote | Dhargaloon, Basooni | 2 | INFRA -I | 196 | 2010-11 | 2021-22 | 25.2 | 2.17 | 0.24 | 2.41
11 | Const. of road from Kainth Gali to H/S behrooti via Fazi Khan Lamnbardar | Ongoing | Poonch | Balakote | Behrooti | 1.5 | INFRA -I | 383.18 | 2011-12 | 2021-22 | 57.74 | 4.5 | 0.5 | 5
12 | Const. of road from Mir Pur to Thak Dharati Pir Gali Balakote | Ongoing | Poonch | Balakote | Mirpur | 2 | INFRA -I | 68.6 | 2013-14 | 2019-20 | 47.6 | 18.9 | 2.1 | 21
13 | Const. of road from 1st more Suyan Katha to Sandote road | Ongoing | Poonch | Balakote | Soyian Katha Sandote | 1.5 | INFRA -I | 125 | 2010-11 | 2021-22 | 34.37 | 4.5 | 0.5 | 5
14 | Const. of Basooni to Hasnal Khanater Dabbi | Ongoing | Poonch | Balakote | Basooni, Hasnal | 2 | INFRA -I | 115 | 2008-09 | 2021-22 | 51 | 4.5 | 0.5 | 5
15 | Const. of Nar road to Gali panchayat Nakka (Kasoyte) | Ongoing | Poonch | Balakote | Nari, Kasyote | 3 | INFRA -I | 84 | 2009-10 | 2021-22 | 32.42 | 4.5 | 0.5 | 5
16 | Const. of road from main road Jaranwali gali to Khala Bhat Sawang Shivling | Ongoing | Poonch | Balakote | Jaranwali Gali, Khala Bhatt | 5 | INFRA -I | 84 | 2010-11 | 2021-22 | 28.945 | 3.6 | 0.4 | 4
17 | Const. of road from Chaki to Mahl Dhargaloon | Ongoing | Poonch | Balakote | Dhargaloon, | 2 | INFRA -I | 36 | 2013-14 | 2020-21 | 11.23 | 1.8 | 0.2 | 2
18 | Upgradtaion of road from 90 Balakoteto Dharat Gali in Extension upto Faizi Khan Mohalla Behrooti | Ongoing | Poonch | Balakote | Behrooti | 1.5 | INFRA -I | 36 | 2014-15 | 2020-21 | 1.65 | 1.8 | 0.2 | 2
19 | Construction of 02 rooms at HS Jaranwali Gali | Ongoing | Poonch | Balakote | Jaranwali Gali | 7 Kms | EDUCATION | 16.5 | 2018-19 | 2020-21 | 4.08 | 2.17 | 0.24 | 2.41
20 | Repair/Renovation of GPS Chitti Bhatti | Ongoing | Poonch | Balakote | Sanjiot | 3 Kms | EDUCATION | 5.2 | 2014-15 | 2019-20 | 4.6 | 0.54 | 0.06 | 0.6
21 | Construction of road Mohalla Magrian,Dhargloon | Ongoing | Poonch | Balakote | Magrian,Dhargloon | Within 10 | INFRA -I | 15.48 | 2019-20 | 2019-20 | 7.74 | 6.97 | 0.77 | 7.74
22 | Const. of Community Hall at Block Head Quarter | New | Poonch | Balakote | Dhargloon Middle | Within 10 | SOCIAL | 10 | 2019-20 | 2020-21 | 0 | 4.5 | 0.5 | 5
23 | Const. of Water Harvesting Tanks | New | Poonch | Balakote | JW Gali, Upper Manjhari, Lower Manjhari, Kallar Morha, Bhata Dhurian, Nar, Sanjiote Upper, Sanjiote Lower, Dhargloon, Dharati, Bharoti | 0-10 | Agriculture | 12 | 2019-20 | 2020-21 | 0 | 5.35 | 0.59 | 5.94
24 | Construction of ACR at Sib loran | New | Poonch | Loran | Loran | 5km | EDUCATION | 21.65 | 2019-20 | 2020-21 | 21.65 | 11.1 | 1.23 | 12.33
25 | Providing water supply to Mohalla Bala and Sib Sarran | Ongoing | Poonch | Mandi | Sib Sarran | 2 Kms | INFRA-II | 43 | 2016-17 | 2021-22 | 9.05 | 0.9 | 0.1 | 1
26 | Const. of MC Uripura | Ongoing | Poonch | Mandi | Uripura | 0-2 Km | HEALTH | 34.56 | 2012-13 | 2019-20 | 28.5 | 5.45 | 0.61 | 6.06
27 | Const. of 1 No. Set of Paramedical Qtr. At PHC Sawjian | Ongoing | Poonch | Mandi | Sawjian | 0-2 Km | HEALTH | 22.34 | 2014-15 | 2020-21 | 10.3 | 1.8 | 0.2 | 2
28 | Construction of 02 rooms at PS Phagwari | Ongoing | Poonch | Mandi | Phagwari | 1 Kms | EDUCATION | 19.44 | 2018-19 | 2019-20 | 7.62 | 10.64 | 1.18 | 11.82
29 | Imp/Mod of Azamabad Khul | Ongoing | Poonch | Mandi | Azamabad | 0-7 | AGRI | 35 | 2015-16 | 2020-21 | 18.1 | 1.8 | 0.2 | 2
30 | Imp/Mod of Jallian Khul | Ongoing | Poonch | Mandi | Jallian | 0-5 | AGRI | 30 | 2014-15 | 2020-21 | 11.58 | 1.8 | 0.2 | 2
31 | Const. of road from Maidan to Gagrian. 1st to 4th | Ongoing | Poonch | Mandi | Maidan, Gagrian | 4 | INFRA -I | 150 | 2004-05 | 2021-22 | 79.47 | 0.9 | 0.1 | 1
32 | Const. of link road to Zairat Thanpeer | Ongoing | Poonch | Mandi | Zairat Thanpeer | 5 | INFRA -I | 160 | 2009-10 | 2021-22 | 30.3 | 0.9 | 0.1 | 1
33 | Const. of link road to Mohalla Pothi Chaktroo | Ongoing | Poonch | Mandi | Pothi Chaktroo | 7 | INFRA -I | 65 | 2012-13 | 2020-21 | 38.99 | 0.9 | 0.1 | 1
34 | Const. of road from Mandi Phagla Main road to Zairat Dogi via High Schol baila | Ongoing | Poonch | Mandi | Baila | 8 | INFRA -I | 173 | 2017-18 | 2021-22 | 0.68 | 2.47 | 0.28 | 2.75
35 | Development of Picnic Spot at Sultan Pathri. | New | Poonch | Mandi | Loran | 2kms | SPL SCHEMES | 10 | 2019-20 | 2020-21 | 0 | 3.6 | 0.4 | 4
36 | Const. of SC Chajjla | Ongoing | Poonch | Mendhar | Chajjla | 0-3 | HEALTH | 94.73 | 2011-12 | 2021-22 | 45.55 | 1.8 | 0.2 | 2
37 | Providing water supply to Moh. Topa Salwah | Ongoing | Poonch | Mendhar | Salwah | 3 Kms | INFRA-II | 35 | 2015-16 | 2020-21 | 18.1 | 0.9 | 0.1 | 1
38 | Providing water supplyu to Moh. Bhatta Chetar | Ongoing | Poonch | Mendhar | Bhatta Chetar | 3 Kms | INFRA-II | 40 | 2017-18 | 2020-21 | 1.28 | 0.9 | 0.1 | 1
39 | Providing water supply to Mohra Mughaid, Keny Chajjla | Ongoing | Poonch | Mendhar | Mughaid | 2 Kms | INFRA-II | 49 | 2017-18 | 2020-21 | 10.61 | 0.9 | 0.1 | 1
40 | Ground levelling of HSS Gahni | Ongoing | Poonch | Mendhar | Gahni | 2 Kms | EDUCATION | 13 | 2018-19 | 2020-21 | 4.08 | 0.9 | 0.1 | 1
41 | Constt. of C/Wall at GMS Phamranar Gursai | Ongoing | Poonch | Mendhar | Gursai | 3 Kms | EDUCATION | 5.25 | 2018-19 | 2019-20 | 2.09 | 2.84 | 0.32 | 3.16
42 | Constt. of C/Wall at GMS Jabran Gursai | Ongoing | Poonch | Mendhar | Gursai | 3 Kms | EDUCATION | 5.65 | 2018-19 | 2019-20 | 2.31 | 3.01 | 0.33 | 3.34
43 | Constt. of C/Wall at GMS Salwaha | Ongoing | Poonch | Mendhar | Salwaha | 4 Kms | EDUCATION | 5.45 | 2018-19 | 2019-20 | 2.3 | 2.83 | 0.32 | 3.15
44 | Constt. of C/Wall at GMS Kalaban | Ongoing | Poonch | Mendhar | Kalaban | 5 Kms | EDUCATION | 5.2 | 2018-19 | 2019-20 | 1.88 | 2.99 | 0.33 | 3.32
45 | Skill Dev.Activities (Basic Computer Fundamental, Driver Cum Mechanic (Men), Driver Cum Mechanic (Women), Electrican (Domestic) & Intergrated Course in Hair, Skin & Makeup) | Ongoing | Poonch | Mendhar | Various Village | 0-10 | SOCIAL | 10 | 2019-20 | 2019-20 | 8.82 | 1.06 | 0.12 | 1.18
46 | Const. of road from Nakka to Salwah. Km 1st to 3rd | Ongoing | Poonch | Mendhar | Naka Salwah | 4 | INFRA -I | 149.58 | 2005-06 | 2020-21 | 116.72 | 0.9 | 0.1 | 1
47 | Upgd. of jeepable road Main road to M.S Dharana Upper | Ongoing | Poonch | Mendhar | Dharana | 1 | INFRA -I | 73 | 2009-10 | 2021-22 | 11.76 | 0.9 | 0.1 | 1
48 | Dharana to Malikpur road km 1st to 5th | Ongoing | Poonch | Mendhar | Dharana, Malikpur | 1.5 | INFRA -I | 330 | 2011-12 | 2021-22 | 33.15 | 0.9 | 0.1 | 1
49 | Const. of road from Awan Charoon to Khanater | Ongoing | Poonch | Mendhar | Awan Charoon, Khanater | 5 | INFRA -I | 379 | 2009-10 | 2021-22 | 285.76 | 4.5 | 0.5 | 5
50 | Link road from PMGSy road to Mohalla Bhramana Ari Plaser including P/wall of Zairat | Ongoing | Poonch | Mendhar | Mendhar | 3 | INFRA -I | 29.5 | 2014-15 | 2020-21 | 9.84 | 0.9 | 0.1 | 1
51 | Suran Mendhar road | Ongoing | Poonch | Mendhar | Suran Mendhar | 4 | INFRA -I | 85 | 2011-12 | 2021-22 | 12.71 | 3.6 | 0.4 | 4
52 | Const. of Ari Sarooti road | Ongoing | Poonch | Mendhar | Sarooti | 3 | INFRA -I | 60 | 2012-13 | 2021-22 | 22.4 | 0.9 | 0.1 | 1
53 | Const. of link road from Ari to Berobian to Chanda Sahib | Ongoing | Poonch | Mendhar | Ari, Berobian | 3 | INFRA -I | 279 | 2010-11 | 2021-22 | 17.75 | 0.45 | 0.05 | 0.5
54 | Extension of road from Jaba to Behra bye pass Mendhar incl. approach road Mendhar Km 1st | Ongoing | Poonch | Mendhar | Jaba Behra | 2.5 | INFRA -I | 169.8 | 2011-12 | 2021-22 | 84.15 | 3.6 | 0.4 | 4
55 | Extension of road from Jaba to behra Bye pass including vented causeway Ari to Dhakki | Ongoing | Poonch | Mendhar | Jaba Behra | 2.5 | INFRA -I | 254 | 2012-13 | 2021-22 | 63.99 | 3.6 | 0.4 | 4
56 | Const . of road from main road to Peer Hyder Shah Chajjla | Ongoing | Poonch | Mendhar | Chajjla | 1.5 | INFRA -I | 84 | 2007-08 | 2021-22 | 37.57 | 4.5 | 0.5 | 5
57 | Const. of road from Dharana Kaloon to Mohalla Hayda Dharana Mendhar | Ongoing | Poonch | Mendhar | Dharana, Kaloon | 1.5 | INFRA -I | 102.5 | 2011-12 | 2021-22 | 5.98 | 0.9 | 0.1 | 1
58 | Const. of road from Sona Gali to Choi Mankote. 3.00 Kms | Ongoing | Poonch | Mendhar | Sona gali Choi Mankote | 2 | INFRA -I | 165 | 2011-12 | 2021-22 | 10.9 | 0.9 | 0.1 | 1
59 | Upgradation and extension of road Behra to Naka Salwah km 3rd & 6th | Ongoing | Poonch | Mendhar | Naka Salwah | 3 | INFRA -I | 185 | 2007-08 | 2021-22 | 46.27 | 0.9 | 0.1 | 1
60 | Const. of road from Harni to Sarooti | Ongoing | Poonch | Mendhar | Harni Sarooti | 3 | INFRA -I | 132.7 | 2011-12 | 2021-22 | 5.5 | 0.9 | 0.1 | 1
61 | Const. of road from Ari to Shamshan Ghat | Ongoing | Poonch | Mendhar | Ari | 3 | INFRA -I | 25 | 2012-13 | 2019-20 | 23.375 | 1.46 | 0.16 | 1.62
63 | Link road Mohalla Baghala harmutha | Ongoing | Poonch | Mendhar | Harmutha | 3.5 | INFRA -I | 45 | 2012-13 | 2020-21 | 3.9 | 0.54 | 0.06 | 0.6
64 | Const. of road by way of E/work in cutting from Dak Bungalow to Golad Km 4th & 5th Rd 0-500 | Ongoing | Poonch | Mendhar | Golad | 1.5 | INFRA -I | 115 | 2014-15 | 2021-22 | 18.2 | 0.9 | 0.1 | 1
65 | Road from Salani to Kagian Kasblari | Ongoing | Poonch | Mendhar | Salani | 4 | INFRA -I | 36 | 2014-15 | 2019-20 | 26.98 | 8.12 | 0.9 | 9.02
66 | Const. of drain main road to Mohalla Breela by way of Balance earthwork in cutting , providing and laying WBm Grade II and III from KM 1st Rd 0-400 | Ongoing | Poonch | Mendhar | Breela | 1.5 | INFRA -I | 45 | 2016-17 | 2020-21 | 7.92 | 0.9 | 0.1 | 1
67 | Const. of Waiting Shed at Ari near S. Ghat | Ongoing | Poonch | Mendhar | Ari | 3 | INFRA -I | 11.83 | 2017-18 | 2019-20 | 0.92 | 9.82 | 1.09 | 10.91
68 | Imp/Mod of Mankote Khul | New | Poonch | Mendhar | Mankote | 3.00 | AGRI | 18 | 2021-20 | 2020-21 | 0 | 8.1 | 0.9 | 9
69 | Construction of B/Wall at PS Khoi Terwan Shahpur | Ongoing | Poonch | Nangali | Shahpur | 1 Kms | EDUCATION | 7 | 2018-19 | 2019-20 | 2.19 | 4.33 | 0.48 | 4.81
70 | Plants Planted/ Fencing on Govt./State Land | Ongoing | Poonch | Poonch | Salotri | 0-5 Km | AGRI | 5 | 2019-20 | 2019-20 | 2.18 | 2.54 | 0.28 | 2.82
71 | Imp./Mod. Of Hillan Khul | Ongoing | Poonch | Poonch | Ajote | 0-2 | AGRI | 30 | 2013-14 | 2019-20 | 27.14 | 2.57 | 0.29 | 2.86
72 | Imp./Mod. Of Jhullas Khul | Ongoing | Poonch | Poonch | Jhullas | 0-2 | AGRI | 62 | 2013-14 | 2021-22 | 10.82 | 0.9 | 0.1 | 1
73 | Construction of road from Noonabandi to India Gate Km 3rd to 4th . | Ongoing | Poonch | Poonch | Noonabandi, India gate | 4 | INFRA -I | 205 | 98-99 | 2019-20 | 204.09 | 0.82 | 0.09 | 0.91
74 | Const. of link road from Sain Baba Mira Sahib to kandyara via nangali | Ongoing | Poonch | Poonch | Kandyara, Nangali | 7 | INFRA -I | 83 | 2001-02 | 2019-20 | 80.2 | 2.52 | 0.28 | 2.8
75 | Const. of link road from Karmara to Defence Post Km 1st | Ongoing | Poonch | Poonch | Karmara | 1 | INFRA -I | 65 | 2007-08 | 2020-21 | 49.21 | 4.5 | 0.5 | 5
76 | Const. of Sain Faqir Din Road to Mohalla Cheran Km3rd | Ongoing | Poonch | Poonch | Kassalian | 2 | INFRA -I | 132 | 2009-10 | 2021-22 | 27.03 | 0.9 | 0.1 | 1
77 | Const of link road Sail to M/S Batwari Khari Km 1st | Ongoing | Poonch | Poonch | Sail, Batwari | 2 | INFRA -I | 76 | 2008-09 | 2021-22 | 29.32 | 2.7 | 0.3 | 3
78 | Const. of link road from Main road to Qazi Mohra via House of GN Mir. L=1Kms | Ongoing | Poonch | Poonch | Qazi Mohra | 6 | INFRA -I | 40 | 2006-07 | 2019-20 | 30.84 | 8.24 | 0.92 | 9.16
79 | Const. of 8M span Culvert over Sukha Katha nallah near madrasa Police Line | Ongoing | Poonch | Poonch | Sukha Katha | 7.5 | INFRA -I | 26 | 2014-15 | 2020-21 | 14.68 | 4.5 | 0.5 | 5
80 | Const. of Dherrian to Degwar Road near High School. Km 1st | Ongoing | Poonch | Poonch | Dheerian, Degwar | 1 | INFRA -I | 70 | 2004-05 | 2020-21 | 51.32 | 3.6 | 0.4 | 4
81 | Link road Mohalla Bilal Kunuyian. (Umar Colony) | Ongoing | Poonch | Poonch | Kunuyian | 7 | INFRA -I | 83.25 | 2005-06 | 2021-22 | 30.67 | 0.9 | 0.1 | 1
82 | Const of link road Mohalan Bakerwala Kunuyian | Ongoing | Poonch | Poonch | Kunuyian | 7 | INFRA -I | 92.5 | 2009-10 | 2021-22 | 11.81 | 0.9 | 0.1 | 1
83 | Const. of Dalhera Link road Km 3rd | Ongoing | Poonch | Poonch | Dalhera | 7 | INFRA -I | 76 | 2010-11 | 2021-22 | 9.78 | 0.45 | 0.05 | 0.5
84 | Main road to Gundi Poonch Km 4th | Ongoing | Poonch | Poonch | Gundi | 5 | INFRA -I | 85 | 2017-18 | 2021-22 | 18.26 | 0.9 | 0.1 | 1
85 | Const. of road from Dehri Sahib to Makki Post Karmara Km 3rd | Ongoing | Poonch | Poonch | Karmara | 1.5 | INFRA -I | 58 | 2017-18 | 2021-22 | 14.78 | 3.28 | 0.36 | 3.64
86 | Const. of link road to HSS Islamabad | Ongoing | Poonch | Poonch | Islamabad | 6 | INFRA -I | 155 | 2019-20 | 2021-22 | 5.8 | 0.9 | 0.1 | 1
87 | Const. of link road from Simluwali Kalai Top to Moorie Duprian Khanater | Ongoing | Poonch | Poonch | Khanater | 9.5 | INFRA -I | 85 | 2018-19 | 2021-22 | 1 | 0.9 | 0.1 | 1
88 | Construction 01 Room in GMS Kasalian | Ongoing | Poonch | Poonch | Kasalian | 1 Kms | EDUCATION | 12 | 2018-19 | 2019-20 | 2.38 | 8.66 | 0.96 | 9.62
89 | Aug. of 33/11 Kv Receving station at Jhulass-I from (2x1.6mva) to (1x3.15Mva ,1x1.6mva) Transformer | New | Poonch | Poonch | Jhulass | 1Kms | SOCIAL | 15 | 2019-20 | 2020-21 | 0 | 8.1 | 0.9 | 9
| Grand Total | [10 empty] | 281.45 | 31.27 | 312.72