## Bandipora
Annual Action Plan for the year 2019-20 under Border Area Development Programme [BADP] - District Bandipore (Amount in Lakhs)
S. No | Name of the Sector/ Scheme / Project | Project Type (New/ On-going) | District | Block | Village | Aerial Distance from LOC/ IB (In Kms) | Sector | Estt. Cost | Year of Commencement | Target for completion | Cum. exp incl. USB 03-2019 | Allocation 2019-20
[12 empty] | Central Share | State Share | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Kashpat Kilshay Road Phase - II (Sedhee Kilshey Checki Beyant) | Ongoing | Bandipora | Gurez | Kilshey | 2 | INFRA-I | 150 | 2014-15 | 2021-22 | 96.45 | 4.5 | 0.5 | 5
2 | Construction of Lanes & Drains at Gurez/ Tulail Ph-II | Ongoing | Bandipora | Gurez | Dawar/ Tulail | 3 | INFRA-I | 150 | 2014-15 | 2021-22 | 93.22 | 4.5 | 0.5 | 5
3 | Const. of Lanes & Drains at Bagtore | Ongoing | Bandipora | Gurez | Bagtore | 2 | INFRA-I | 150 | 2014-15 | 2020-21 | 131.18 | 3.6 | 0.4 | 4
4 | Widening of Dangerous Road Stretches in Gurez/ Tulail | Ongoing | Bandipora | Gurez | Dawar/ Tulail | 2 | INFRA-I | 100 | 2014-15 | 2020-21 | 64.6 | 3.6 | 0.4 | 4
5 | Upg of Way Side (Country Type) facility at Zuthkuchi | Ongoing | Bandipora | Gurez | Zuthkuchi | 4 | INFRA-I | 25 | 2016-17 | 2020-21 | 13 | 3.6 | 0.4 | 4
6 | Construction of Fencing & Dev. Of Lawn of Rest House Badugam | Ongoing | Bandipora | Gurez | Badugam | 1 | OTHER INFRA | 25 | 2018-19 | 2020-21 | 5 | 3.6 | 0.4 | 4
7 | Constt. of 5 Roomed GMS Building at Neeru | Ongoing | Bandipora | Gurez | Neeru | 3 | EDUCATION | 47.18 | 2016-17 | 2019-20 | 43.18 | 3.6 | 0.4 | 4
8 | Constt. of 5 Roomed GPS Building at Dassi B (Shifted to Izmerg) | Ongoing | Bandipora | Gurez | Dassi | 5 | EDUCATION | 43.18 | 2016-17 | 2020-21 | 30.44 | 4.5 | 0.5 | 5
9 | Constt. of 5 Roomed Addl. Accmd. For HSS Izmerg shifted to HSS Baduab for resi. Qtr. For teachers | Ongoing | Bandipora | Gurez | Izmerg | 5 | EDUCATION | 43.18 | 2018-19 | 2021-22 | 7 | 3.6 | 0.4 | 4
10 | Constt. of 5 Roomed Addl. Accmd. For HS Wanpora (Shifted to MS Dangithal) | Ongoing | Bandipora | Gurez | Wanpora | 3 | EDUCATION | 43.18 | 2018-19 | 2021-22 | 7 | 3.6 | 0.4 | 4
11 | Constt. of 5 Roomed Addl. Accmd. For HSS Baduab | Ongoing | Bandipora | Gurez | Baduab | 2 | EDUCATION | 43.18 | 2018-19 | 2021-22 | 7 | 3.6 | 0.4 | 4
12 | 3 Beded Hospital at Baduab | Ongoing | Bandipora | Gurez | Baduab | 2 | HEALTH | 82 | 2016-17 | 2021-22 | 39.97 | 4.5 | 0.5 | 5
13 | Medical Aid centre at Kilshay | Ongoing | Bandipora | Gurez | Kilshay | 0.5 | HEALTH | 25 | 2016-17 | 2019-20 | 20.98 | 3.618 | 0.402 | 4.02
14 | CB Net Analyzer Single Module SDH Dawar | Ongoing | Bandipora | Gurez | Dawar | 3 | HEALTH | 16 | 2018-19 | 2019-20 | 4 | 10.8 | 1.2 | 12
15 | Construction of 75 Mt Capacity Food Godown at Kilshay & 25 Mt of Capacity at Koragbal | Ongoing | Bandipora | Gurez | Kilshay/Koragbal | 2 | OTHER INFRA | 65.42 | 2016-17 | 2021-22 | 35.49 | 4.5 | 0.5 | 5
16 | Construction of 75 Mt Capacity Food Godown each at Abdullin & Hussangam | Ongoing | Bandipora | Gurez | Abdullin /Hussangam | 2 | OTHER INFRA | 89.54 | 2016-17 | 2021-22 | 41.61 | 3.6 | 0.4 | 4
17 | Construction of 75 Mt Capacity Food Godown each at Khandyal and Jalindora | Ongoing | Bandipora | Gurez | Khandyal and Jalindora | 2 | OTHER INFRA | 57.92 | 2016-17 | 2020-21 | 37.07 | 3.6 | 0.4 | 4
18 | Construction of 75 Mt Capacity Food Godown each at Wazirthal & Nayal | Ongoing | Bandipora | Gurez | Wazirthal & Nayal | 2 | OTHER INFRA | 75 | 2017-18 | 2021-22 | 16.29 | 4.5 | 0.5 | 5
19 | Electrification of Wazirthal Village by connecting with 200KVA DG Set Badugam | Ongoing | Bandipora | Gurez | Badugam | 3 | OTHER INFRA | 28.5 | 2016-17 | 2019-20 | 25.04 | 3.114 | 0.346 | 3.46
20 | Electrification of Blow-neil, Skinder & Safeed-Aab Villages. | Ongoing | Bandipora | Gurez | Blow-neil, Skinder & Safeed-Aab | 3 | OTHER INFRA | 30 | 2018-19 | 2020-21 | 7 | 4.5 | 0.5 | 5
21 | Electrification of Village Badugam by way of Supply, Installation, Testing & Commissioning of 250 KVA DG Set at Badugam Tulail. | Ongoing | Bandipora | Gurez | Badugam | 3 | OTHER INFRA | 26 | 2018-19 | 2019-20 | 15 | 9.9 | 1.1 | 11
22 | Sheds for DG Sets (Civil Works) at Markote, Kashpot, Jalindora, T-Kilshay, Checkwali and Wazirthal | Ongoing | Bandipora | Gurez | Markote Kashpot JalindoraT-Kilshay Checkwali and Wazirthal | 2 | OTHER INFRA | 50.5 | 2017-18 | 2019-230 | 40.73 | 8.793 | 0.977 | 9.77
23 | Construction of DG Shed at Gujran Mir Mohalla | Ongoing | Bandipora | Gurez | Gujran | 3 | OTHER INFRA | 15 | 2017-18 | 2019-20 | 7.79 | 6.489 | 0.721 | 7.21
24 | Providing of Drinking Water Supply to different schools in Gurez area. | Ongoing | Bandipora | Gurez | Gurez | 2 | INFRA-II | 32.98 | 2017-18 | 2020-21 | 12.47 | 3.78 | 0.42 | 4.2
25 | WSS Nai-Basti Zadgay | Ongoing | Bandipora | Gurez | Zadgay | 2 | INFRA-II | 55.5 | 2018-19 | 2021-22 | 11 | 4.5 | 0.5 | 5
26 | WSS Qureshippora Manzgund | Ongoing | Bandipora | Gurez | Manzgund | 2 | INFRA-II | 54.3 | 2018-19 | 2021-22 | 11 | 4.5 | 0.5 | 5
27 | Veterinary Centre at Kilshay (Shifted to PTL) | Ongoing | Bandipora | Gurez | Kilshay | 0.5 | AGRI | 23.5 | 2016-17 | 2019-20 | 17.43 | 5.463 | 0.607 | 6.07
28 | Skill Development (Handicrafts) | Ongoing | Bandipora | Gurez | Gurez | 0.5 | SOCIAL | 7.5 | 2018-19 | 2019-20 | 2.5 | 4.5 | 0.5 | 5
29 | Skill Development (ITI gurez) | Ongoing | Bandipora | Gurez | Gurez | 0.5 | SOCIAL | 9.94 | 2018-19 | 2019-20 | 4.94 | 4.5 | 0.5 | 5
30 | Constr.of addl.accomodation for PHC Badugam | New | Bandipora | Gurez | Badugam | 2 | HEALTH | 40 | 2019-20 | 2021-22 | 0 | 15.27 | 1.7 | 16.97
| Grand Total: | [10 empty] | 152.727 | 16.973 | 169.7