## AAP 2019-20 (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
42 | Creation of 02 Nos of 100 KVA sub station at Salamabad,Uri | New | Baramulla | Uri | Salamabad,Uri | 2 | SOCIAL | 16 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 14.4 | 1.6 | 16 | 0 | 0 | 0 | No | 2 | To be completed durring 2019-20 | 0
43 | Creation of 63 KVA substation 4 Nos at Dawaran,Dardkote,Kamalkote and Garkot | New | Baramulla | Uri | Dawaran,Dardkote,Kamalkote,Garkote, | 3 | SOCIAL | 20 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 18 | 2 | 20 | 0 | 0 | 0 | No | 4 | To be completed durring 2019-20 | 0
44 | Augmentation 63KVA to 100KVA at Dawara and Augmentation 100KVA to 200KVA 1 No | New | Baramulla | Uri | Dawara | 3 | SOCIAL | 7.5 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 6.3 | 0.7 | 7 | 0 | 0 | 0 | No | 2 | To be completed durring 2019-20 | 0.5
61 | Creation 63 KVA Sub Station at Girdanawa Boniyar | New | Baramulla | Boniyar | Girdanawa | 6 | SOCIAL | 4.5 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 3.42 | 0.38 | 3.8 | 0.279 | 0.031 | 0.31 | No | 1 | To be completed durring 2019-20 | 0.39
70 | Const. of Deep Drain at Shahi hamdan colony Khawaja Bagh | New | Baramulla | Baramulla | Khawajabagh | 8 | INFRA- I | 18 | 2019-20 | 2020-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 5.4 | 0.6 | 6 | 1.8 | 0.2 | 2 | RM | Drain=100 | New Work | 10
71 | upgradation of Binner Khadora road by way of grade 1st(km 2nd Rd100 to 290 mtr) grade 2nd (km 1st to km 2nd Rd 200 mtr | New | Baramulla | Baramulla | Khadoora binner | 8 | INFRA- I | 8.96 | 2019-20 | 2020-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.96 | 2.7 | 0.3 | 3 | 2.331 | 0.259 | 2.59 | KM | WBM=1.00 | New Work | 3.37
72 | Const. of Road from Forest Hut Kawaherbala to Kawaher Payeen | New | Baramulla | Baramulla | Kawher | 7 | INFRA- I | 21 | 2019-20 | 2021-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 3.6 | 0.4 | 4 | 2.7 | 0.3 | 3 | KM RM RM | FW/G-I=0.50 Wall=50 Pipes=25 | New Work | 14
78 | Creation of 100 Kva 05 Nos at Jalsheeri,Kaliaban,Gntamulla and Near jamia Masjid Toiba Ushkura | New | Baramulla | Baramulla | Jalsheeri,Kaliaban,Gntamulla and Ushkura | 9 | SOCIAL | 16.65 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.65 | 14.4 | 1.6 | 16 | 0 | 0 | 0 | No | 5 | To be completed durring 2019-20 | 0.65
79 | Augmenation of 100 KVA to 200 KV sub station 02 No's at Sachliwaran, Zogiyar | New | Baramulla | Baramulla | Sachliwaran, Zogiyar | 9 | SOCIAL | 12 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 9.9 | 1.1 | 11 | 0 | 0 | 0 | No | 2 | To be completed durring 2019-20 | 1
81 | Const. of Road from Hachipora to Zethan Via Hr. Secondary School | New | Baramulla | Rafiabad | Hachipora,Zethan | 5 | INFRA- I | 50 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 27 | 3 | 30 | 14.4 | 1.6 | 16 | Cum KM No: RM | EW=5000 WBM=5.00 cul=01 Pipes=20 | To be completed durring 2019-20 | 4
82 | Const. of link Road to ChanMohalla and Sheikh Mohalla at Pazalla | New | Baramulla | Rafiabad | Pazalpora | 6 | INFRA- I | 20 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 9 | 1 | 10 | 4.5 | 0.5 | 5 | KM RM | WBM=2.00 Pipes=25 | To be completed durring 2019-20 | 5
83 | Const. Of inner links at Rawocha | New | Baramulla | Rafiabad | Rawoocha | 8 | INFRA- I | 20 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 9 | 1 | 10 | 4.5 | 0.5 | 5 | KM RM | WBM=2.00 Pipes=25 | To be completed durring 2019-20 | 5
84 | Const. of Sheikhpora Hapatnar Road | New | Baramulla | Rafaiabad | Sheikhpora | 7 | INFRA- I | 25 | 2019-20 | 2020-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 9.14 | 1.02 | 10.16 | 3.6 | 0.4 | 4 | Cum RM KM | EW=500 Pipes=25 WBM=2.00 | New Work | 10.84
85 | Upgradation road from Dangiwacaha to Reshipora | New | Baramulla | Rafaiabad | Dagiwacaha | 8 | INFRA- I | 20 | 2019-20 | 2020-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2.7 | 0.3 | 3 | 3.546 | 0.394 | 3.94 | KM RM | WBM=1.00 Pipes=20 | New Work | 13.06
87 | Creation of 100 KVA Sub Stations 3 Nos at Kiterdaji,Kangroosa,Tangmulla((Sheikh Mohalla Kumar) ) | New | Baramulla | Rafiabad | Kiterdaji,Kangroosa,Tangmulla((Sheikh Mohalla Kumar) ) | 5 | SOCIAL | 16.65 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.65 | 14.97 | 1.66 | 16.63 | 0 | 0 | 0 | No | 3 | To be completed durring 2019-20 | 0.02
88 | Creation of 63 KVA Sub Stations 3 Nos at Dalri,Karila, Roowcha (Bilal Colony) | New | Baramulla | Rafiabad | Dalri,Karila, Roowcha (Bilal Colony) | 5 | SOCIAL | 15.5 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 13.95 | 1.55 | 15.5 | 0 | 0 | 0 | No | 3 | To be completed durring 2019-20 | 0
89 | Augmentation 63KVA to 100 KVA sub station 3Nos at Bakhipora, Chanam, Pazalpora | New | Baramulla | Rafiabad | Bakhipora, Chanam, Pazalpora | 7 | SOCIAL | 7.5 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 6.75 | 0.75 | 7.5 | 0 | 0 | 0 | No | 3 | To be completed durring 2019-20 | 0
97 | upgradation of road from Braman to Larianagan | New | Baramulla | Rohama | Lariangan, Braman | 5 | INFRA- I | 35 | 2019-20 | 2020-2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 13.5 | 1.5 | 15 | 4.5 | 0.5 | 5 | KM RM | WBM=3.0 Pipes=30 | new work | 15
103 | Creation of 2 No of 100 KVA sub station at Sarbal colony (Budden), Hamdina Colony Nadihal and Augmentation 2 Nos of 63KVA to 100KVA at Balhama, Ladoora | New | Baramulla | Rohama | bundan, Nadihal, Balhama,Ladoora | 7 | SOCIAL | 22 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 16.2 | 1.8 | 18 | 3.096 | 0.344 | 3.44 | No | 4 | To be Completed durring 2019-20 | 0.56
104 | Improvement of main 11 KVA HT line from Janbazapora to Binner | New | Baramulla | Rohama | Binner, venkara | 7 | SOCIAL | 5 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3.09 | 0.34 | 3.43 | 0 | 0 | 0 | No, Km | 20, 1.00 | To be Completed durring 2019-20 | 1.57
111 | Creation of 04 No of 100 KVA sub station at Choutipatri, Ganibaba, Chopan Mohalla Batoo,Bhat Mohalla Katipora | New | Baramulla | Tangmarg |  | 6 | SOCIAL | 17 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 8.84 | 0.98 | 9.82 | 5.562 | 0.618 | 6.18 | No | 5 | To be Completed durring 2019-20 | 1
118 | Creation of sub 05 No. of Sub station at Muran Tangawari, Dungdara, Bed Check Kreeri, Watergam and Vizer. | New | Baramulla | Wagoora | Muran Tangawari, Dungdara, Bed Check Kreeri, Watergam and Vizer. | 8 | SOCIAL | 24.77 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.77 | 22.29 | 2.48 | 24.77 | 0 | 0 | 0 | No. | 5 |  | 0
119 | Augumentation of 100 KVA to 200 KVA sub station at at Sidique Colony Authoora | New | Baramulla | Wagoora | Sidique Colony Authoora | 9 | SOCIAL | 6 | 2019-20 | 2019-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5.4 | 0.6 | 6 | 0 | 0 | 0 | No | 1 |  | 0
|  | New/ Ongoing | District | Block | Village | in Km |  | Rs in Lac |  |  | Convergenec | BADP | Total |  | C.S | S.S | TOTAL |  | C.S | S.S | Total | C.S | S.S | Total | Unit( Km/mtr/sqtmtr/ No. Acrs | Value
113 | Constt. of Nilsar-Takia Yousuf Shah Wahizabal road | on going | Baramulla | Wagoora | Nilsar/ Takia Yousuf shah | 6 | INFRA- I | 133.62 | 2015-16 | 2023-24 | 0 | 37.47 | 37.47 | 0 | 9.81 | 1.09 | 10.9 | 85.25 | 5.4 | 0.6 | 6 | 6.3 | 0.7 | 7 | KM Cum RM | WBM=1.50 EW=2500 Pipes=30 | work in progress | 72.25
114 | Constt. of link road Kachwa - Masjid Angan | on going | Baramulla | Wagoora | Kachwa/Masjid Anagan | 10 | INFRA- I | 152.55 | 2015-16 | 2023-24 | 0 | 37.55 | 37.55 | 0 | 9.11 | 1.01 | 10.12 | 104.88 | 6.69 | 0.74 | 7.43 | 6.3 | 0.7 | 7 | KM RM RM | WBM=1.75 Pipes=25 Wall=40 | work in progress | 90.45
115 | Waripora Waza Mohalla- Parray Mohalla Suchlipora road | on going | Baramulla | Wagoora | Waripora / Suchlipora | 8 | INFRA- I | 98.08 | 2015-16 | 2023-24 | 0 | 35.01 | 35.01 | 0 | 9.81 | 1.09 | 10.9 | 52.17 | 9 | 1 | 10 | 6.3 | 0.7 | 7 | KM RM RM | WBM=2.00 Pipes=25 Wall=50 | work in progress | 35.17
116 | Sherkhan patti-Shirpora Beigh Pati road | on going | Baramulla | Wagoora | Shirpora | 7 | INFRA- I | 162.98 | 2015-16 | 2023-24 | 0 | 26.55 | 26.55 | 0 | 9.11 | 1.01 | 10.12 | 126.31 | 5.4 | 0.6 | 6 | 6.3 | 0.7 | 7 | KM RM | WBM=2.00 Pipes=15 | work in progress | 113.31
117 | Putnar Saloosa road | on going | Baramulla | Wagoora | Saloosa | 10 | INFRA- I | 80 | 2016-17 | 2023-24 | 0 | 31.26 | 31.26 | 0 | 9.81 | 1.09 | 10.9 | 37.84 | 9.45 | 1.05 | 10.5 | 5.931 | 0.659 | 6.59 | KM RM | WBM=1.75 Pipes=20 | work in progress | 20.75
62 | Upgd. Of Rajpora link road | on going | Baramulla | Baramulla | Rajpora | 7 | INFRA- I | 80 | 2011-12 | 2020-21 | 0 | 28.89 | 28.89 | 0 | 8.15 | 0.91 | 9.06 | 42.05 | 9 | 1 | 10 | 3.6 | 0.4 | 4 | KM RM | WBM=1.50 Drain=40 | work in progress | 28.05
63 | Upgrd. Of rad from High School Vohultra to Arkhwari | on going | Baramulla | Baramulla | Vohlutra | 8 | INFRA- I | 30 | 2015-16 | 2020-21 | 0 | 5.64 | 5.64 | 0 | 0.21 | 0.02 | 0.23 | 24.13 | 3.6 | 0.4 | 4 | 1.8 | 0.2 | 2 | Km | WBM=1.00 | Work in progress | 18.13
64 | Inner Links at Jalsheeri Baramulla | on going | Baramulla | Baramulla | Jalsheeri | 8 | INFRA- I | 70 | 2017-18 | 2023-24 | 0 | 6.9 | 6.9 | 0 | 8.6 | 0.96 | 9.56 | 53.54 | 7.2 | 0.8 | 8 | 1.8 | 0.2 | 2 | Km RM RM | WBM=1.25 Pipes=9 Wall=30 | work in progress | 43.54
65 | Const. of Sochalwarn Road | on going | Baramulla | Baramulla | Sochalwarn | 8 | INFRA- I | 46 | 2018-19 | 2021-22 | 0 | 3 | 3 | 0 | 2.7 | 0.3 | 3 | 40 | 6.3 | 0.7 | 7 | 4.5 | 0.5 | 5 | KM RM RM | WBM=1.25 Wall=50 Drain=50 | work in progress | 28
66 | Const. of Bhat Mohalla Bandipayeen Road and C/o Drain With Path | on going | Baramulla | Baramulla | Bandipayeen | 7 | INFRA- I | 50 | 2018-19 | 2021-22 | 0 | 5 | 5 | 0 | 4.5 | 0.5 | 5 | 40 | 5.4 | 0.6 | 6 | 4.5 | 0.5 | 5 | KM RM RM | WBM=1.00 Wall=50 Drain=50 | work in progress | 29
67 | Const. of 1st Floor Of Hr. Seconadary School Fatehgrah | on going | Baramulla | Baramulla | Fathegrah | 9 | INFRA- I | 30 | 2018-19 | 2021-22 | 0 | 5 | 5 | 0 | 4.5 | 0.5 | 5 | 20 | 4.5 | 0.5 | 5 | 4.5 | 0.5 | 5 |  |  | work in progress | 10
68 | Const Of Building At Hr. Secondary School Khaitangan | on going | Baramulla | Baramulla | Khaitangan | 9 | INFRA- I | 50 | 2018-19 | 2021-22 | 0 | 4 | 4 | 0 | 3.76 | 0.42 | 4.18 | 41.82 | 9 | 1 | 10 | 4.5 | 0.5 | 5 |  |  | work in progress | 26.82
69 | Const./Devlopment of Play Field at Hr. Seconaday School Chandoosa Phase II | on going | Baramulla | Baramulla | Chandoosa | 8 | INFRA- I | 15 | 2018-19 | 2018-19 | 0 | 3 | 3 | 0 | 2.7 | 0.3 | 3 | 9 | 1.8 | 0.2 | 2 | 0.9 | 0.1 | 1 | Cum | EW=150 | completed and closed | 6
73 | Constt. Of 15000 Gallon Capacity Service Reservoir at Katianwali (WSS Katianwali) | on going | Baramulla | Baramulla | Kitianwali | 9 | INFRA- II | 27.41 | 2013-14 | 2021-22 | 0 | 8.91 | 8.91 | 0 | 4.87 | 0.43 | 5.3 | 13.2 | 8.36 | 0.93 | 9.29 | 0 | 0 | 0 | No |  | work in progress | 3.91
74 | Const. of 0.15 Galon SR at Patchar | on going | Baramulla | Baramulla | Patchar | 8 | INFRA- II | 99.04 | 2013-14 | 2022-23 | 0 | 9.12 | 9.12 | 0 | 3.68 | 0.41 | 4.09 | 85.83 | 4.5 | 0.5 | 5 | 0 | 0 | 0 | No |  | work in progress | 80.83
75 | Const. of R/Wall at Kalas Nowgama Main Pipe Line | on going | Baramulla | Baramulla | Nowgam | 7 | INFRA- II | 5 | 2018-19 | 2019-20 | 0 | 0 | 0 | 0 | 1.8 | 0.2 | 2 | 3 | 2.7 | 0.3 | 3 | 0 | 0 | 0 | No | 1 | To be completed | 0
76 | Constt. of Adminsitrative block at PHC Sheeri | on going | Baramulla | Baramulla | Sheeri | 8 | HEALTH | 68.41 | 2013-14 | 2021-22 | 0 | 25.25 | 25.25 | 0 | 4.96 | 0.55 | 5.51 | 37.65 | 4.5 | 0.5 | 5 | 4.5 | 0.5 | 5 | No |  | work in progress | 27.65
77 | Construction of Sub Centre with ANM Residence at Kanispora | on going | Baramulla | Baramulla | Kansipora | 10 | HEALTH | 39 | 2014-15 | 2020-21 | 0 | 6.74 | 6.74 | 0 | 9.3 | 0.2 | 9.5 | 22.76 | 9 | 1 | 10 | 8.1 | 0.9 | 9 | No |  | work in progress | 3.76
86 | Development of Lavender Park at Rafiabad | on going | Baramulla | Rafiabad | Kiterdaji | 4 | AGRI | 30 | 2018-19 | 2019-20 | 0 | 0 | 0 | 0 | 4.5 | 0.5 | 5 | 25 | 18 | 2 | 20 | 4.5 | 0.5 | 5 | No. | 1 | to be completed | 0
91 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | on going | Baramulla | Rafiabad | All villages of Particular Block are eligible | 7 |  | 33.61 |  |  | 0 | 9.72 | 9.72 | 0 | 17.26 | 0.81 | 18.07 | 5.82 | 5.24 | 0.58 | 5.82 | 0 | 0 | 0 |  |  |  | 0
92 | Constt. of 9m span bridge at Takiya (Hamdub) | on going | Baramulla | Rohama | Hamdub | 6 | INFRA- I | 56.65 | 2011-12 | 2017-18 | 0 | 48.4 | 48.4 | 0 | 1.8 | 0.2 | 2 | 6.25 | 4.5 | 0.5 | 5 | 0.9 | 0.1 | 1 | No: | Cul. = 1 | Complitioin cost to be closed | 0.25
93 | Inner links at Ladu Ladoora | on going | Baramulla | Rohama | Ladu | 6 | INFRA- I | 42.17 | 2015-16 | 2020-21 | 0 | 10.76 | 10.76 | 0 | 0.56 | 0.06 | 0.62 | 30.79 | 4.5 | 0.5 | 5 | 1.8 | 0.2 | 2 |  |  | Work in Progress | 23.79
94 | Road from Rohama to Patoosa via Water Reservioir | on going | Baramulla | Rohama | Rohama, Patoosa | 7 | INFRA- I | 40 | 2015-16 | 2020-21 | 0 | 9.19 | 9.19 | 0 | 0.67 | 0.07 | 0.74 | 30.07 | 4.5 | 0.5 | 5 | 1.8 | 0.2 | 2 |  |  | Work in Progress | 23.07
95 | Khamoh Inner links | on going | Baramulla | Rohama | Khamoh | 6 | INFRA- I | 30 | 2016-17 | 2021-22 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 9 | 1 | 10 | KM RM | WBM=1.25 Pipe=10 | closed | 15
96 | Takiya Panziwara road | on going | Baramulla | Rohama | Panziwara | 6 | INFRA- I | 5 | 2017-18 | 2019-20 | 0 | 1.1 | 1.1 | 0 | 0.23 | 0.02 | 0.25 | 3.65 | 2.7 | 0.3 | 3 | 0 | 0 | 0 | KM | WBM=0.30 | To be completed | 0.65
99 | Earth filling near Masjid Sharief Hamambal Rohama | on going | Baramulla | Rohama | Hamambal | 8 | OTHER INFRA | 3 | 2017-18 | 2018-19 | 0 | 1.72 | 1.72 | 0 | 0.35 | 0 | 0.35 | 0.93 | 0.32 | 0.04 | 0.36 | 0 | 0 | 0 |  |  | completed | 0.57
100 | Constrution of Lanes and Drains at Various Spots of Rohama Block | on going | Baramulla | Rohama | Rohama, Valanwar,Doniwari | 8 | OTHER INFRA | 30 | 2018-19 | 2019-20 | 0 | 0 | 0 | 0 | 17.1 | 1.9 | 19 | 11 | 9.9 | 1.1 | 11 | 0 | 0 | 0 |  |  | To be completed durring 2019-20 | 0
101 | Providing of Water Supply to Khamoha | on going | Baramulla | Rohama | Khamoha | 5 | INFRA- II | 10 | 2018-19 | 2019-20 | 0 | 0 | 0 | 0 | 4.5 | 0.5 | 5 | 5 | 4.5 | 0.5 | 5 | 0 | 0 | 0 | No. | 1 | To be completed | 0
102 | Constt. of Sub Centre at Naribal | on going | Baramulla | Tangmarg | Naribal | 3 |  | 30 | 2017-18 | 2020-21 | 0 | 8.87 | 8.87 | 0 | 10.2 | 0.8 | 11 | 10.13 | 5.4 | 0.6 | 6 | 3.6 | 0.4 | 4 | No. | 1 | To be completed durring 2019-20 | 0.13
105 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | on going | Baramulla | Rohama | All villages of Particular Block are eligible | 6 | SOOCIAL | 19.39 |  |  | 0 | 4.56 | 4.56 | 0 | 10.4 | 0.53 | 10.93 | 3.9 | 3.51 | 0.39 | 3.9 | 0 | 0 | 0 |  |  |  | 0
106 | Hayatpora Rawatpora road | on going | Baramulla | Tangmarg | Rawatpora | 7 | INFRA- I | 75 | 2011-12 | 2020-21 | 0 | 24.33 | 24.33 | 0 | 0 | 0 | 0 | 50.67 | 9 | 1 | 10 | 1.8 | 0.2 | 2 | KM RM RM | WBM=2.00 Pipes=15 wall=50 | Work in progress | 38.67
107 | Constt. Of road from Ferozpora to Check Treran via Check Ferzopora incld. Sheikh Mohalla | on going | Baramulla | Tangmarg | Ferozpora | 7 | INFRA- I | 75 | 2015-16 | 2021-22 | 0 | 5.39 | 5.39 | 0 | 0 | 0 | 0 | 69.61 | 7.2 | 0.8 | 8 | 1.8 | 0.2 | 2 | KM RM RM | WBM=1.50 Pipes=15 Wall=30 | Work in progress | 59.61
108 | Upgrd. Of Bonagam Ratnipora road | on going | Baramulla | Tangmarg | Ratnipora | 8 | INFRA- I | 33 | 2012-13 | 2022-23 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 27 | 6.3 | 0.7 | 7 | 2.7 | 0.3 | 3 | KM RM | WBM=1.50 Pipes=40 | Work in progress | 17
109 | Construction of Sub Centre with ANM Residence at Gogaldara | on going | Baramulla | Tangmarg | Gogaldara | 3 | HEALTH | 39 | 2016-17 | 2022-23 | 0 | 15.95 | 15.95 | 0 | 2.5 | 0.28 | 2.78 | 20.27 | 4.5 | 0.5 | 5 | 0.9 | 0.1 | 1 | No. |  | work in progress | 14.27
110 | Construction of Sub Centre with ANM Residence at Wahigund | on going | Baramulla | Tangmarg | Wahigund | 5 | HEALTH | 39 | 2016-17 | 2019-20 | 0 | 16.1 | 16.1 | 0 | 7.5 | 0.28 | 7.78 | 15.12 | 9 | 1 | 10 | 4.5 | 0.5 | 5 | No. |  | to be completed | 0.12
112 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | on going | Baramulla | Tangmarg | All villages of Particular Block are eligible | 6 | SOCIAL | 7.96 |  |  | 0 | 4.65 |  | 0 | 5.47 | 0.29 | 5.76 | 2.2 | 1.98 | 0.22 | 2.2 | 0 | 0 | 0 |  |  |  | 0
120 | Augumentation of to WSS Hail by way of tapping of additional source (Spring) through pipe network and construction of addtional clear Water Sump at existing Pump Station Hail. | on going | Baramulla | Wagoora | Hail | 9 | INFRA- II | 40 | 2016-17 |  | 0 | 20.52 | 20.52 | 0 | 9.19 | 1.02 | 10.21 | 9.27 | 6.3 | 0.7 | 7 | 0 | 0 | 0 | No |  | Work in progress | 2.27
121 | Construction of 2 No. Zonal SR's of 0.25 lac gallan capacity each at higher contour of Sheikhpora and Putuhar incld. Laying fitting of clear water main and supply main | on going | Baramulla | Wagoora | Khaipora | 3 | INFRA- II | 65 | 2016-17 |  | 0 | 20.12 | 20.12 | 0 | 4.32 | 0.48 | 4.8 | 40.08 | 5.4 | 0.6 | 6 | 0 | 0 | 0 | No |  | Work in progress | 34.08
122 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | on going | Baramulla | Wagoora | All villages of Particular Block are eligible |  | SOCIAL | 10.2 |  |  | 0 | 0 | 0 | 0 | 5.14 | 0.56 | 5.7 | 4.5 | 4.05 | 0.45 | 4.5 | 0 | 0 | 0 |  |  |  | 0
1 | Const. of link road from Shadara road to Chuntry/Chain link fencing HSS Sultandaki | ongoing | Baramulla | Uri | Chuntry | 0.5 | INFRA- I | 65 | 2007-08 | 2019-20 | 0 | 58.47 | 58.47 | 0 | 4.29 | 1.1 | 5.39 | 1.14 | 1.03 | 0.11 | 1.14 | 0 | 0 | 0 | mtrs | WBM=200 | To be Completed durring 2019-20 | 0
2 | Construction of road Sarai to Jaba | ongoing | Baramulla | Uri | Jaba | 1 | INFRA- I | 35 | 2011-12 | 2018-19 | 0 | 30.071 | 30.071 | 0 | 3.12 | 0.35 | 3.47 | 1.459 | 1.26 | 0.14 | 1.4 | 0 | 0 | 0 | RM | wall=20 | To be Completed durring 2019-20 | 0.059
3 | Constt. Of link road to Chapper | ongoing | Baramulla | Uri | Chapper | 1 | INFRA- I | 65 | 2014-15 | 2020-21 | 0 | 23.41 | 23.41 | 0 | 3.33 | 0.37 | 3.7 | 37.89 | 9 | 1 | 10 | 0 | 0 | 0 |  |  | work in progress | 27.89
4 | Constt. Of Sultan Daki link road | ongoing | Baramulla | Uri | Sultan Daki | 2 | INFRA- I | 65 | 2007-08 | 2019-20 | 0 | 49.23 | 49.23 | 0 | 4.23 | 0.47 | 4.7 | 11.07 | 9.9 | 1.1 | 11 | 0 | 0 | 0 | Km RM | WBM=1.50 Wall=40 | completion cost to be closed | 0.07
5 | Constt. Of link road from Kundi to Rama | ongoing | Baramulla | Uri | Kundi | 1 | INFRA- I | 40 | 2015-16 | 2019-20 | 0 | 17.14 | 17.14 | 0 | 4.45 | 0.49 | 4.94 | 17.92 | 9 | 1 | 10 | 4.5 | 0.5 | 5 | RM RM | Wall=40 Pipes=20 | completion cost to be closed | 2.92
6 | Upgrd. Of Shahkote Limber road | ongoing | Baramulla | Uri | Limber | 3 | INFRA- I | 150 | 2015-16 | 2021-22 | 0 | 77.24 | 77.24 | 0 | 23.75 | 2.64 | 26.39 | 46.37 | 9 | 1 | 10 | 3.6 | 0.4 | 4 | Km RM | WBM=1.50 Wall=75 | work in progress | 32.37
7 | Constt. of Nlayan to Kathar at Dara Gutliyan | ongoing | Baramulla | Uri | Dara Gutliyan | 3 | INFRA- I | 30 | 2016-17 | 2019-20 | 0 | 12.25 | 12.25 | 0 | 5.08 | 0.56 | 5.64 | 12.11 | 7.2 | 0.8 | 8 | 3.6 | 0.4 | 4 | Km RM | WBM=1.25 Wall=60 | to be completed | 0.11
8 | Constt. of main road Choolan to Takiya at Daragutliyan | ongoing | Baramulla | Uri | Choolan | 1 | INFRA- I | 60 | 2016-17 | 2022-23 | 0 | 8.45 | 8.45 | 0 | 4.3 | 0.48 | 4.78 | 46.77 | 4.5 | 0.5 | 5 | 3.6 | 0.4 | 4 | Km RM | WBM=1.00 Wall=50 | work in progress | 37.77
9 | Constt. of road from PMGSY road to Kashmiri Mohalla Kalgai Uri | ongoing | Baramulla | Uri | Kalgai | 3 | INFRA- I | 35 | 2016-17 | 2019-20 | 0 | 9.14 | 9.14 | 0 | 3.55 | 0.38 | 3.93 | 21.93 | 4.5 | 0.5 | 5 | 4.5 | 0.5 | 5 | Km RM | WBM=1.00 Wall=55 | completion cost to be closed | 11.93
10 | Constt. of road from Salalmabad Uri to Gujjar Pati | ongoing | Baramulla | Uri | Salamabad | 4 | INFRA- I | 40 | 2016-17 | 2022-23 | 0 | 11.83 | 11.83 | 0 | 4.58 | 0.51 | 5.09 | 23.08 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | Km RM | WBM=1.00 Wall=40 | work in progress | 15.58
11 | Constt. of road from Jabla to Harian | ongoing | Baramulla | Uri | Jabla | 3 | INFRA- I | 35 | 2016-17 | 2019-20 | 0 | 12.9 | 12.9 | 0 | 5 | 0.56 | 5.56 | 16.54 | 9 | 1 | 10 | 2.7 | 0.3 | 3 | Km RM | WBM=1.40 Wall=60 | to be completed | 3.54
12 | Constt. of road from Thalla to Birjala | ongoing | Baramulla | Uri | Thala | 0 | INFRA- I | 60 | 2016-17 | 2022-23 | 0 | 9.18 | 9.18 | 0 | 4.2 | 0.47 | 4.67 | 46.15 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | Km RM | WBM=1.00 Wall=40 | work in progress | 38.65
13 | Constt./Upgrd. Of Thala to Jabda road | ongoing | Baramulla | Uri | Jabda | 1 | INFRA- I | 80 | 2016-17 | 2022-23 | 0 | 8.14 | 8.14 | 0 | 3.55 | 0.38 | 3.93 | 67.93 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | Km RM | WBM=1.00 Wall=40 | work in progress | 60.43
14 | Constt. of Mugal mohalla to Kalgai Thala link | ongoing | Baramulla | Uri | Kalgai | 3 | INFRA- I | 90 | 2017-18 | 2022-23 | 0 | 4.14 | 4.14 | 0 | 4.44 | 0.48 | 4.92 | 80.94 | 4.5 | 0.5 | 5 | 1.8 | 0.2 | 2 | mtrs RM | WBM=750 Wall=40 | work in progress | 73.94
15 | Constt. of road from Madian to Jabda via Alaphinda | ongoing | Baramulla | Uri | Jabda | 1 | INFRA- I | 90 | 2017-18 | 2022-23 | 0 | 4.49 | 4.49 | 0 | 5.41 | 0.6 | 6.01 | 79.5 | 9 | 1 | 10 | 4.5 | 0.5 | 5 | Km RM | WBM=1.50 Wall=60 | work in progress | 64.5
16 | Constt. of road from Dachi main road to Muqam incld. Upper Dachi | ongoing | Baramulla | Uri | Dachi | 3 | INFRA- I | 75 | 2017-18 | 2022-23 | 0 | 5.52 | 5.52 | 0 | 5.62 | 0.63 | 6.25 | 63.23 | 9 | 1 | 10 | 4.5 | 0.5 | 5 | Km RM | WBM=1.50 Wall=60 | work in progress | 48.23
17 | Constt. of road from main Choolan to Lower gingle | ongoing | Baramulla | Uri | Choolan | 1 | INFRA- I | 57 | 2017-18 | 2022-23 | 0 | 6.21 | 6.21 | 0 | 7.56 | 0.84 | 8.4 | 42.39 | 6.3 | 0.7 | 7 | 2.25 | 0.25 | 2.5 | mtr Cum RM | WBM=500 EW=400 Wall=75 | work in progress | 32.89
18 | Constt. of PMGSY road to High School Zamboor Pattan Link | ongoing | Baramulla | Uri | Choolan | 1 | INFRA- I | 60 | 2017-18 | 2022-23 | 0 | 5.52 | 5.52 | 0 | 4.72 | 0.53 | 5.25 | 49.23 | 5.4 | 0.6 | 6 | 1.8 | 0.2 | 2 | mtr Cum RM | WBM=500 EW=300 Wall=50 | work in progress | 41.23
19 | Road from Thajal PMGSY road to Food Store | ongoing | Baramulla | Uri | Thajal | 1 | INFRA- I | 25 | 2017-18 | 2022-23 | 0 | 4.14 | 4.14 | 0 | 4.44 | 0.49 | 4.93 | 15.93 | 5.4 | 0.6 | 6 | 1.35 | 0.15 | 1.5 | Cum RM | EW=250 Wall=150 |  | 8.43
20 | Constt. of main road uri to Lower Uri upto College Ground | ongoing | Baramulla | Uri | Uri | 5 | INFRA- I | 50 | 2017-18 | 2022-23 | 0 | 4.14 | 4.14 | 0 | 4.44 | 0.49 | 4.93 | 40.93 | 4.5 | 0.5 | 5 | 0 | 0 | 0 | Cum RM | EW=350 Wall=100 | work in progress | 35.93
21 | Const. of PMGSY road to Bani | ongoing | Baramulla | Uri | Bani | 1 | INFRA- I | 114 | 2017-18 | 2022-23 | 0 | 5.52 | 5.52 | 0 | 4.72 | 0.52 | 5.24 | 103.24 | 9 | 1 | 10 | 2.25 | 0.25 | 2.5 | Km RM | WBM=1.50 Wall=60 | work in progress | 90.74
22 | Const. Of PMGSY road to Jabla link road | ongoing | Baramulla | Uri | Jabla | 2 | INFRA- I | 40 | 2017-18 | 2022-23 | 0 | 3.45 | 3.45 | 0 | 4.3 | 0.48 | 4.78 | 31.77 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | Km RM | WBM=0.70 Wall=60 | work in progress | 24.27
23 | Widening / Extension of Bandi Dayar link road | ongoing | Baramulla | Uri | Dayar | 5 | INFRA- I | 76 | 2017-18 | 2022-23 | 0 | 5.52 | 5.52 | 0 | 4.72 | 0.53 | 5.25 | 65.23 | 9 | 1 | 10 | 2.25 | 0.25 | 2.5 | Km RM | WBM=1.00 Wall=80 | work in progress | 52.73
24 | Constt. of link road from Beacon road to Sheikh Mohalla Gingle-Uri | ongoing | Baramulla | Uri | Gingle | 4 | INFRA- I | 33 | 2017-18 | 2022-23 | 0 | 5.52 | 5.52 | 0 | 5.62 | 0.63 | 6.25 | 21.23 | 4.5 | 0.5 | 5 | 1.8 | 0.2 | 2 | Cum RM | EW=450 Wall=100 | work in progress | 14.23
25 | Const. of link road from National High Way upto Bhat Mohalla Nowpora Salamabad | ongoing | Baramulla | Uri | Slamabad | 4 | INFRA- I | 35 | 2017-18 | 2022-24 | 0 | 0 | 0 | 0 | 6.85 | 0.14 | 6.99 | 28.01 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | Cum RM | EW=300 Wall=100 | work in progress | 20.51
26 | Constr. Of Main road Choolan to Gali Daragutliyan. | ongoing | Baramulla | Uri | Daragutliyan | 3 | INFRA- I | 57.25 | 2018-19 | 2024-25 | 0 | 0 | 0 | 0 | 2.7 | 0.3 | 3 | 54.25 | 4.5 | 0.5 | 5 | 2.7 | 0.3 | 3 | Cum RM | EW=500 Wall=100 | work in progress | 46.25
27 | Construction of road from R&B Store to Brinjan. | ongoing | Baramulla | Uri | Brijan | 3 | INFRA- I | 50 | 2018-19 | 2024-25 | 0 | 0 | 0 | 0 | 1.8 | 0.2 | 2 | 48 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | Km RM | WBM=1.20 Wall=30 | work in progress | 40.5
28 | Constr. Of road from Main road Zamboor Pattan Shukrlari to Bani | ongoing | Baramulla | Uri | Bani | 3 | INFRA- I | 48.05 | 2018-19 | 2024-25 | 0 | 0 | 0 | 0 | 1.98 | 0.22 | 2.2 | 45.85 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | Km Cum | WBM=1.00 EW=300 | work in progress | 38.35
29 | Constr. Of road from Main road Naganari to Chakan. | ongoing | Baramulla | Uri | Chakan | 4 | INFRA- I | 40 | 2018-19 | 2024-25 | 0 | 0 | 0 | 0 | 2.25 | 0.25 | 2.5 | 37.5 | 4.5 | 0.5 | 5 | 1.35 | 0.15 | 1.5 | Km Cum | WBM=1.00 EW=100 | work in progress | 31
30 | Constr. Of Mughal road to Mir Mohalla Pringle. | ongoing | Baramulla | Uri | Pringle | 4 | INFRA- I | 15 | 2018-19 | 2019-20 | 0 | 0 | 0 | 0 | 1.8 | 0.2 | 2 | 13 | 1.8 | 0.2 | 2 | 0 | 0 | 0 | mtr | WBM=300 | completion cost to be closed | 11
31 | Constr. Of Mir Mohalla Link road at Mayan. | ongoing | Baramulla | Uri | Mayan | 5 | INFRA- I | 45 | 2018-19 | 2019-20 | 0 | 0 | 0 | 0 | 1.8 | 0.2 | 2 | 43 | 4.5 | 0.5 | 5 | 2.7 | 0.3 | 3 | Cum RM | EW=500 Wall=100 | completion cost to be closed | 35
32 | Constr. Of link road from Dakan to Lohar/ Chachi/ Bhat Mohalla | ongoing | Baramulla | Uri | Dakan | 4 | INFRA- I | 95 | 2018-19 | 2024-25 | 0 | 0 | 0 | 0 | 1.82 | 0.2 | 2.02 | 92.98 | 9 | 1 | 10 | 4.5 | 0.5 | 5 | Cum RM | EW=5000 Wall=250 | work in progress | 77.98
33 | Constr. Of Main road Ghati to Ghati Mohalla at Daragutliyan. | ongoing | Baramulla | Uri | Daragutliyan | 3 | INFRA- I | 56 | 2018-19 | 2024-25 | 0 | 0 | 0 | 0 | 1.81 | 0.2 | 2.01 | 53.99 | 7.2 | 0.8 | 8 | 4.5 | 0.5 | 5 | Cum RM | EW=5000 Wall=150 | work in progress | 40.99
34 | WSS Karoone | ongoing | Baramulla | Uri | Karoone | 4 | INFRA- II | 40 | 2016-17 | 2022-23 | 0 | 3.45 | 3.45 | 0 | 3.42 | 0.38 | 3.8 | 32.75 | 9 | 1 | 10 | 3.6 | 0.4 | 4 | No |  | work in progress | 18.75
35 | WSS Fatehwali | ongoing | Baramulla | Uri | Fatehwali | 4 | INFRA- II | 30 | 2016-17 | 2022-23 | 0 | 2.76 | 2.76 | 0 | 3.26 | 0.36 | 3.62 | 23.62 | 9 | 1 | 10 | 6.813 | 0.757 | 7.57 | No |  | work in progress | 6.05
36 | WSS Deccan (Ward 7 & 8) | ongoing | Baramulla | Uri | Deccan | 4 | INFRA- II | 35 | 2016-17 | 2022-23 | 0 | 2.76 | 2.76 | 0 | 6.26 | 0.36 | 6.62 | 25.62 | 10.8 | 1.2 | 12 | 3.6 | 0.4 | 4 | No |  | work in progress | 9.62
37 | Improvement / Extension of of WSS Gingle ,Dawaran and Zamboor Pattan | ongoing | Baramulla | Uri | Gingle | 4 | INFRA- II | 30 | 2016-17 | 2020-21 | 0 | 6.9 | 6.9 | 0 | 4.55 | 0.51 | 5.06 | 18.04 | 7.2 | 0.8 | 8 | 3.6 | 0.4 | 4 | No |  | work in progress | 6.04
38 | Mohra Khandewan Khul | ongoing | Baramulla | Uri | Mohra | 3 | AGRI | 20 | 2016-17 | 2020-21 | 0 | 4.5 | 4.5 | 0 | 4.03 | 0.45 | 4.48 | 11.02 | 7.2 | 0.8 | 8 | 2.7 | 0.3 | 3 | No | 1 | To be Completd | 0.02
39 | Construction of Sub Centre with ANM Residence at Basgran Uri | ongoing | Baramulla | Uri | Basgran | 2 | HEALTH | 42.74 | 2016-17 | 2019-20 | 0 | 15.12 | 15.12 | 0 | 7.15 | 0.79 | 7.94 | 19.68 | 9 | 1 | 10 | 8.1 | 0.9 | 9 | No | 1 | To be completed durring 2019-20 | 0.68
40 | Construction of Sub Centre with ANM Residence at Salamabad Uri | ongoing | Baramulla | Uri | Salamabad | 4 | HEALTH | 42.74 | 2016-17 | 2019-20 | 0 | 15.59 | 15.59 | 0 | 7.15 | 0.79 | 7.94 | 19.21 | 10.48 | 1.16 | 11.64 | 6.3 | 0.7 | 7 | No | 1 | To be completed durring 2019-21 | 0.57
41 | Construction of Sub Centre with ANM Residence at Dardkote Uri | ongoing | Baramulla | Uri | Salamabad | 4 | HEALTH | 42.74 | 2016-17 | 2019-20 | 0 | 14.98 | 14.98 | 0 | 7.13 | 0.79 | 7.92 | 19.84 | 5.4 | 0.6 | 6 | 11.7 | 1.3 | 13 | No | 1 | To be completed durring 2019-22 | 0.84
45 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | ongoing | Baramulla | Uri | All villages of Particular Block are eligible |  | SOCIAL | 87.72 |  |  | 0 | 24.7 | 24.7 | 0 | 46 | 2.02 | 48.02 | 15 | 13.5 | 1.5 | 15 | 0 | 0 | 0 |  |  |  | 0.01
46 | Const. of road from Pehlipora to Ijara. | ongoing | Baramulla | Boniyar | Ijara | 5 | INFRA- I | 80 | 2003-04 | 2019-20 | 0 | 49.236 | 49.236 | 0 | 2.15 | 0.24 | 2.39 | 28.374 | 3.6 | 0.4 | 4 | 0.9 | 0.1 | 1 | km | WBM=1.0 | Completion cost for closure | 23.374
47 | Constr. Of road from Four Bay to Paden Bimyar | ongoing | Baramulla | Boniyar | Bimyar | 6 | INFRA- I | 45.04 | 2006-07 | 2019-20 | 0 | 38.226 | 38.226 | 0 | 2.6 | 0.29 | 2.89 | 3.924 | 2.25 | 0.25 | 2.5 | 0.45 | 0.05 | 0.5 | Rm | Wall=49 | Completion cost for closure | 0.924
48 | Const. of Batangi link road | ongoing | Baramulla | Boniyar | Batangi | 2 | INFRA- I | 21.5 | 2009-10 | 2017-18 | 0 | 15.88 | 15.88 | 0 | 2.53 | 0.28 | 2.81 | 2.81 | 1.8 | 0.2 | 2 | 0.45 | 0.05 | 0.5 | Rm | drain=40 | Completion cost for closure | 0.31
49 | Const. of road from Reshiwari to Jabdar. | ongoing | Baramulla | Boniyar | Jabda | 1 | INFRA- I | 45 | 2009-10 | 2020-21 | 0 | 29.71 | 29.71 | 0 | 0.35 | 0.04 | 0.39 | 14.9 | 2.7 | 0.3 | 3 | 0.9 | 0.1 | 1 | KM | FW=0.70 | Work in progress | 10.9
50 | Const. of Nowshera Khuhalan road | ongoing | Baramulla | Boniyar | Nowshera | 7 | INFRA- I | 45 | 2010-11 | 2021-22 | 0 | 10.82 | 10.82 | 0 | 1.49 | 0.17 | 1.66 | 32.52 | 0 | 0 | 0 | 1.8 | 0.2 | 2 | mtr | WBM=400 | Work in progress | 30.52
51 | Constrution of road from Dumping to Bacchi | ongoing | Baramulla | Boniyar | Bacchi | 5 | INFRA- I | 42 | 2010-11 | 2021-22 | 0 | 18.28 | 18.28 | 0 | 2.08 | 0.23 | 2.31 | 21.41 | 4.5 | 0.5 | 5 | 2.7 | 0.3 | 3 | mtr RM | WBM=500 Wall=20 | Work in progress | 13.41
52 | Extesion of Gujjar Nar Dazna road at Lachipora | ongoing | Baramulla | Boniyar | Lachipora | 3 | INFRA- I | 35 | 2014-15 | 2020-21 | 0 | 6.07 | 6.07 | 0 | 1.35 | 0.15 | 1.5 | 27.43 | 2.7 | 0.3 | 3 | 1.8 | 0.2 | 2 | mtr Cum | WBM=300 GSB=150 | Work in progress | 22.43
53 | Constt. Of inner links at Peer Mohalla Batangi Boniyar | ongoing | Baramulla | Boniyar | Batangi | 5 | INFRA- I | 40 | 2015-16 | 2022-23 | 0 | 6.49 | 6.49 | 0 | 1.04 | 0.12 | 1.16 | 32.35 | 0 | 0 | 0 | 1.35 | 0.15 | 1.5 | mtr | WBM=250 | Work in progress | 30.85
54 | Constt. of road from Bijhama to Jabdar | ongoing | Baramulla | Boniyar | Bojhama | 3 | INFRA- I | 37 | 2013-14 | 2022-23 | 0 | 4.925 | 4.925 | 0 | 1.56 | 0.17 | 1.73 | 30.345 | 1.8 | 0.2 | 2 | 0.9 | 0.1 | 1 | mtr | WBM=500 Wall=20 | Work in progress | 27.345
55 | Constt. of Khan Mohalla to Bijimber road | ongoing | Baramulla | Boniyar | Bijimber | 3 | INFRA- I | 80 | 2016-17 | 2022-23 | 0 | 4.77 | 4.77 | 0 | 0.35 | 0.04 | 0.39 | 74.84 | 0 | 0 | 0 | 2.7 | 0.3 | 3 | mtr RM RM | WBM=750 Wall=10 Pipes=10 | Work in progress | 71.84
56 | Bachilari Khul | ongoing | Baramulla | Boniyar | Bachilari | 6 | AGRI | 40 | 2016-17 | 2023-24 | 0 | 5.39 | 5.39 | 0 | 2.72 | 0.3 | 3.02 | 31.59 | 2.01 | 0.22 | 2.23 | 0 | 0 | 0 | No. |  | Work in progress | 29.36
57 | Limber Tethmulla Khul | ongoing | Baramulla | Boniyar | Limber | 6 | AGRI | 50 | 2016-17 | 2023-24 | 0 | 3.91 | 3.91 | 0 | 2.36 | 0.26 | 2.62 | 43.47 | 1.97 | 0.22 | 2.19 | 0 | 0 | 0 | No. |  | Work in progress | 41.28
58 | Irrigation Khul Lachipora B | ongoing | Baramulla | Boniyar | Lachipora | 5 | AGRI | 90 | 2017-18 | 2023-24 | 0 | 0.28 | 0.28 | 0 | 4.59 | 0.51 | 5.1 | 84.62 | 1.97 | 0.22 | 2.19 | 0 | 0 | 0 | No. |  | Work in progress | 82.43
59 | WSS Hiller Larri | ongoing | Baramulla | Boniyar | Larri | 4 | INFRA- II | 80 | 2016-17 | 2023-24 | 0 | 5.19 | 5.19 | 0 | 3.54 | 0.39 | 3.93 | 70.88 | 4.5 | 0.5 | 5 | 2.25 | 0.25 | 2.5 | No |  | Work in progress | 63.38
60 | Construction of Sub Centre with ANM Residence at Ahtishampora | ongoing | Baramulla | Boniyar | Ahtishampora | 5 | HEALTH | 42.74 | 2016-17 | 2019-20 | 0 | 11.65 | 11.65 | 0 | 10.73 | 0.49 | 11.22 | 19.87 | 10.8 | 1.2 | 12 | 1.8 | 0.2 | 2 | No | 1 | To be completed durring 2019-20 | 5.87
98 | Development of Lavender Park at Rafiabad | ongoing | Baramulla | Rohama | Venkara | 7 |  | 30 | 2018-19 | 2019-20 | 0 |  |  | 0 | 4.5 | 0.5 | 5 | 25 | 13.5 | 1.5 | 15 | 9 | 1 | 10 | No | 1 | to be completed | 0
80 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses |  | Baramulla | Baramulla | All villages of Particular Block are eligible | 8 | SOCIAL | 26.6 |  |  | 0 | 10.98 | 10.98 | 0 | 9.82 | 0.7 | 10.52 | 5.1 | 4.59 | 0.51 | 5.1 | 0 | 0 | 0 |  |  |  | 0
90 | Const. of Lanes and Drains at Various Spots of Rafiabad Block |  | Baramulla | Rafiabad |  | 7 | OTHER INFRA | 38 | 2018-19 | 2019-20 | 0 | 0 | 0 | 0 | 20.7 | 2.3 | 23 | 15 | 0 | 0 | 0 | 10.24 | 1.14 | 11.38 |  |  | To be completed durring 2019-20 | 3.62
| G. TOTAL | [6 empty] | 5494.22 |  |  |  | 1185.858 | 1181.208 | 0 | 524.71 | 49.81 | 574.52 | 3738.492 | 788.41 | 87.59 | 876 | 314.098 | 34.902 | 349 | 0 | 48 | 0
[21 empty] | 889.01 |  |  | 349
2.99

## Baramulla
ANNUAL ACTION PLAN BADP 2019-20 DISTRICT BARAMULLA (Rs. In Lakhs)
S No | Name of the Scheme / Project | Project Type New/ Ongoing | District | Block | Village | Distance from LOC/IB (Kms) | Sector | Estd. cost | Year of Start | Target Year of Compl-etion | Cumm. Exp incl USB 03/20189 | Allocation 2019-20
[12 empty] | C.S | S.S | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 17 | 18 | 19
1 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | ongoing | Baramulla | Baramulla | All villages of Particular Block are eligible | 8 | SOCIAL | 26.6 | 2017-18 | 2019-20 | 21.5 | 4.59 | 0.51 | 5.1
2 | Upgd. Of Rajpora link road | ongoing | Baramulla | Baramulla | Rajpora | 7 | INFRA- I | 80 | 2011-12 | 2021-22 | 37.95 | 4.5 | 0.5 | 5
3 | Upgrd. Of rad from High School Vohultra to Arkhwari | ongoing | Baramulla | Baramulla | Vohlutra | 8 | INFRA- I | 30 | 2015-16 | 2020-21 | 5.87 | 3.6 | 0.4 | 4
4 | Inner Links at Jalsheeri Baramulla | ongoing | Baramulla | Baramulla | Jalsheeri | 8 | INFRA- I | 70 | 2017-18 | 2021-22 | 16.46 | 5.81 | 0.65 | 6.46
5 | Const. of Sochalwarn Road | ongoing | Baramulla | Baramulla | Sochalwarn | 8 | INFRA- I | 46 | 2018-19 | 2021-22 | 6 | 6.3 | 0.7 | 7
6 | Const. of Bhat Mohalla Bandipayeen Road and C/o Drain With Path | ongoing | Baramulla | Baramulla | Bandipayeen | 7 | INFRA- I | 50 | 2018-19 | 2021-22 | 10 | 5.4 | 0.6 | 6
7 | Const. of 1st Floor Of Hr. Seconadary School Fatehgrah | ongoing | Baramulla | Baramulla | Fathegrah | 9 | INFRA- I | 30 | 2018-19 | 2020-21 | 10 | 4.5 | 0.5 | 5
8 | Const Of Building At Hr. Secondary School Khaitangan | ongoing | Baramulla | Baramulla | Khaitangan | 9 | INFRA- I | 50 | 2018-19 | 2021-22 | 8.18 | 4.5 | 0.5 | 5
9 | Const./Devlopment of Play Field at Hr. Seconaday School Chandoosa Phase II | ongoing | Baramulla | Baramulla | Chandoosa | 8 | INFRA- I | 15 | 2018-19 | 2020-21 | 6 | 1.8 | 0.2 | 2
10 | Constt. Of 15000 Gallon Capacity Service Reservoir at Katianwali (WSS Katianwali) | ongoing | Baramulla | Baramulla | Kitianwali | 9 | INFRA- II | 27.41 | 2013-14 | 2019-20 | 14.21 | 11.88 | 1.32 | 13.2
11 | Const. of 0.15 Galon SR at Patchar | ongoing | Baramulla | Baramulla | Patchar | 8 | INFRA- II | 99.04 | 2013-14 | 2021-22 | 13.21 | 4.5 | 0.5 | 5
12 | Const. of R/Wall at Kalas Nowgama Main Pipe Line | ongoing | Baramulla | Baramulla | Nowgam | 7 | INFRA- II | 5 | 2018-19 | 2019-20 | 2 | 2.7 | 0.3 | 3
13 | Constt. of Adminsitrative block at PHC Sheeri | ongoing | Baramulla | Baramulla | Sheeri | 8 | HEALTH | 68.41 | 2013-14 | 2021-22 | 30.76 | 4.5 | 0.5 | 5
14 | Construction of Sub Centre with ANM Residence at Kanispora | ongoing | Baramulla | Baramulla | Kansipora | 10 | HEALTH | 39 | 2014-15 | 2020-21 | 16.24 | 4.5 | 0.5 | 5
15 | Const. of Road from Forest Hut Kawaherbala to Kawaher Payeen | New | Baramulla | Baramulla | Kawher | 7 | INFRA- I | 21 | 2019-20 | 2020-21 | 0 | 7.68 | 0.85 | 8.53
16 | Const. of road from Pehlipora to Ijara. | ongoing | Baramulla | Boniyar | Ijara | 5 | INFRA- I | 80 | 2003-04 | 2021-22 | 51.626 | 1.8 | 0.2 | 2
17 | Constr. Of road from Four Bay to Paden Bimyar | ongoing | Baramulla | Boniyar | Bimyar | 6 | INFRA- I | 45.04 | 2006-07 | 2019-20 | 41.12 | 3.53 | 0.39 | 3.92
18 | Const. of Batangi link road | ongoing | Baramulla | Boniyar | Batangi | 2 | INFRA- I | 21.5 | 2009-10 | 2019-20 | 18.69 | 2.53 | 0.28 | 2.81
19 | Const. of road from Reshiwari to Jabdar. | ongoing | Baramulla | Boniyar | Jabda | 1 | INFRA- I | 45 | 2009-10 | 2020-21 | 30.1 | 1.8 | 0.2 | 2
20 | Const. of Nowshera Khuhalan road | ongoing | Baramulla | Boniyar | Nowshera | 7 | INFRA- I | 45 | 2010-11 | 2021-22 | 12.48 | 0.9 | 0.1 | 1
21 | Constrution of road from Dumping to Bacchi | ongoing | Baramulla | Boniyar | Bacchi | 5 | INFRA- I | 42 | 2010-11 | 2021-22 | 20.59 | 2.7 | 0.3 | 3
22 | Extesion of Gujjar Nar Dazna road at Lachipora | ongoing | Baramulla | Boniyar | Lachipora | 3 | INFRA- I | 35 | 2014-15 | 2020-21 | 7.57 | 2.7 | 0.3 | 3
23 | Constt. Of inner links at Peer Mohalla Batangi Boniyar | ongoing | Baramulla | Boniyar | Batangi | 5 | INFRA- I | 40 | 2015-16 | 2021-22 | 7.65 | 0.9 | 0.1 | 1
24 | Constt. of road from Bijhama to Jabdar | ongoing | Baramulla | Boniyar | Bojhama | 3 | INFRA- I | 37 | 2013-14 | 2021-22 | 6.655 | 1.8 | 0.2 | 2
25 | Constt. of Khan Mohalla to Bijimber road | ongoing | Baramulla | Boniyar | Bijimber | 3 | INFRA- I | 80 | 2016-17 | 2022-23 | 5.16 | 0.9 | 0.1 | 1
26 | Bachilari Khul | ongoing | Baramulla | Boniyar | Bachilari | 6 | AGRI | 40 | 2016-17 | 2021-22 | 8.41 | 2.01 | 0.22 | 2.23
27 | Limber Tethmulla Khul | ongoing | Baramulla | Boniyar | Limber | 6 | AGRI | 50 | 2016-17 | 2021-22 | 6.53 | 1.97 | 0.22 | 2.19
28 | Irrigation Khul Lachipora B | ongoing | Baramulla | Boniyar | Lachipora | 5 | AGRI | 90 | 2017-18 | 2022-23 | 5.38 | 1.97 | 0.22 | 2.19
29 | WSS Hiller Larri | ongoing | Baramulla | Boniyar | Larri | 4 | INFRA- II | 80 | 2016-17 | 2022-23 | 9.12 | 1.33 | 0.15 | 1.48
30 | Construction of Sub Centre with ANM Residence at Ahtishampora | ongoing | Baramulla | Boniyar | Ahtishampora | 5 | HEALTH | 42.74 | 2016-17 | 2020-21 | 22.87 | 2.7 | 0.3 | 3
31 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | ongoing | Baramulla | Rafaiabad | All villages of Particular Block are eligible | 7 | SOCIAL | 33.61 | 2016-17 | 2019-20 | 27.79 | 5.24 | 0.58 | 5.82
32 | Const. of Lanes and Drains at Various Spots of Rafiabad Block | Ongoing | Baramulla | Rafaiabad | Rafiaabad block | 7 | OTHER INFRA | 38 | 2018-19 | 2019-20 | 23 | 13.5 | 1.5 | 15
33 | Const. of Road from Hachipora to Zethan Via Hr. Secondary School | New | Baramulla | Rafaiabad | Hachipora,Zethan | 5 | INFRA- I | 50 | 2019-20 | 2021-22 | 0 | 14.85 | 1.65 | 16.5
34 | Const. Of inner links at Rawocha | New | Baramulla | Rafaiabad | Rawoocha | 8 | INFRA- I | 20 | 2019-20 | 2020-21 | 0 | 6.3 | 0.7 | 7
35 | Creation of 63 KVA Sub Stations 3 Nos at Dalri,Karila, Roowcha (Bilal Colony) | New | Baramulla | Rafaiabad | Dalri,Karila, Roowcha (Bilal Colony) | 5 | SOCIAL | 15.5 | 2019-20 | 2019-20 | 0 | 13.95 | 1.55 | 15.5
36 | Providing of Water Supply to Khamoha | ongoing | Baramulla | Rohama | Khamoha | 5 | INFRA- II | 10 | 2018-19 | 2019-20 | 5 | 4.5 | 0.5 | 5
37 | Constt. of 9m span bridge at Takiya (Hamdub) | ongoing | Baramulla | Rohama | Hamdub | 6 | INFRA- I | 56.65 | 2011-12 | 2019-20 | 50.4 | 5.62 | 0.63 | 6.25
38 | Inner links at Ladu Ladoora | ongoing | Baramulla | Rohama | Ladu | 6 | INFRA- I | 42.17 | 2015-16 | 2021-22 | 11.38 | 1.8 | 0.2 | 2
39 | Road from Rohama to Patoosa via Water Reservioir | ongoing | Baramulla | Rohama | Rohama, Patoosa | 7 | INFRA- I | 40 | 2015-16 | 2021-22 | 9.93 | 1.8 | 0.2 | 2
40 | Khamoh Inner links | ongoing | Baramulla | Rohama | Khamoh | 6 | INFRA- I | 30 | 2016-17 | 2021-22 | 5 | 1.8 | 0.2 | 2
41 | Takiya Panziwara road | ongoing | Baramulla | Rohama | Panziwara | 6 | INFRA- I | 5 | 2017-18 | 2019-20 | 1.35 | 3.29 | 0.36 | 3.65
42 | Constrution of Lanes and Drains at Various Spots of Rohama Block | ongoing | Baramulla | Rohama | Rohama, Valanwar,Doniwari | 8 | OTHER INFRA | 30 | 2018-19 | 2019-20 | 19 | 9.9 | 1.1 | 11
43 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | ongoing | Baramulla | Rohama | All villages of Particular Block are eligible | 6 | SOOCIAL | 19.39 | 2016-17 | 2019-20 | 15.49 | 3.51 | 0.39 | 3.9
44 | Upgradation of road from Braman to Larianagan | New | Baramulla | Rohama | Lariangan, Braman | 5 | INFRA- I | 35 | 2019-20 | 2020-21 | 0 | 17.51 | 1.94 | 19.45
45 | Hayatpora Rawatpora road | ongoing | Baramulla | Tangmarg | Rawatpora | 7 | INFRA- I | 75 | 2011-12 | 2021-22 | 24.33 | 4.5 | 0.5 | 5
46 | Constt. Of road from Ferozpora to Check Treran via Check Ferzopora incld. Sheikh Mohalla | ongoing | Baramulla | Tangmarg | Ferozpora | 7 | INFRA- I | 75 | 2015-16 | 2021-22 | 5.39 | 2.88 | 0.32 | 3.2
47 | Upgrd. Of Bonagam Ratnipora road | ongoing | Baramulla | Tangmarg | Ratnipora | 8 | INFRA- I | 33 | 2012-13 | 2021-22 | 6 | 3.6 | 0.4 | 4
48 | Construction of Sub Centre with ANM Residence at Gogaldara | ongoing | Baramulla | Tangmarg | Gogaldara | 3 | HEALTH | 39 | 2016-17 | 2020-21 | 18.73 | 4.5 | 0.5 | 5
49 | Construction of Sub Centre with ANM Residence at Wahigund | ongoing | Baramulla | Tangmarg | Wahigund | 5 | HEALTH | 39 | 2016-17 | 2020-21 | 23.88 | 4.5 | 0.5 | 5
50 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | ongoing | Baramulla | Tangmarg | All villages of Particular Block are eligible | 6 | SOCIAL | 12.61 | 2016-17 | 2019-20 | 10.41 | 1.98 | 0.22 | 2.2
51 | Constt. of Sub Centre at Naribal | ongoing | Baramulla | Tangmarg | Naribal | 3 | HEALTH | 30 | 2017-18 | 2019-20 | 19.87 | 9.12 | 1.01 | 10.13
52 | Creation of 03 No of 100 KVA sub station at Choutipatri, Ganibaba and Bhat Mohalla Katipora | New | Baramulla | Tangmarg | Katlipora | 6 | SOCIAL | 12.75 | 2019-20 | 2020-21 | 0 | 3.6 | 0.4 | 4
53 | Const. of link road from Shadara road to Chuntry/Chain link fencing HSS Sultandaki | ongoing | Baramulla | Uri | Chuntry | 0.5 | INFRA- I | 65 | 2007-08 | 2019-20 | 63.86 | 1.03 | 0.11 | 1.14
54 | Construction of road Sarai to Jaba | ongoing | Baramulla | Uri | Jaba | 1 | INFRA- I | 35 | 2011-12 | 2019-20 | 33.541 | 1.31 | 0.15 | 1.46
55 | Constt. Of link road to Chapper | ongoing | Baramulla | Uri | Chapper | 1 | INFRA- I | 65 | 2014-15 | 2020-21 | 27.11 | 4.5 | 0.5 | 5
56 | Constt. Of Sultan Daki link road | ongoing | Baramulla | Uri | Sultan Daki | 2 | INFRA- I | 65 | 2007-08 | 2019-20 | 53.93 | 9.96 | 1.11 | 11.07
57 | Constt. Of link road from Kundi to Rama | ongoing | Baramulla | Uri | Kundi | 1 | INFRA- I | 40 | 2015-16 | 2020-21 | 22.08 | 4.5 | 0.5 | 5
58 | Upgrd. Of Shahkote Limber road | ongoing | Baramulla | Uri | Limber | 3 | INFRA- I | 150 | 2015-16 | 2021-22 | 103.63 | 4.5 | 0.5 | 5
59 | Constt. of Nlayan to Kathar at Dara Gutliyan | ongoing | Baramulla | Uri | Dara Gutliyan | 3 | INFRA- I | 30 | 2016-17 | 2020-21 | 17.89 | 3.6 | 0.4 | 4
60 | Constt. of main road Choolan to Takiya at Daragutliyan | ongoing | Baramulla | Uri | Choolan | 1 | INFRA- I | 60 | 2016-17 | 2021-22 | 13.23 | 4.5 | 0.5 | 5
61 | Constt. of road from PMGSY road to Kashmiri Mohalla Kalgai Uri | ongoing | Baramulla | Uri | Kalgai | 3 | INFRA- I | 35 | 2016-17 | 2020-21 | 13.07 | 4.5 | 0.5 | 5
62 | Constt. of road from Salalmabad Uri to Gujjar Pati | ongoing | Baramulla | Uri | Salamabad | 4 | INFRA- I | 40 | 2016-17 | 2020-21 | 16.92 | 4.5 | 0.5 | 5
63 | Constt. of road from Jabla to Harian | ongoing | Baramulla | Uri | Jabla | 3 | INFRA- I | 35 | 2016-17 | 2020-21 | 18.46 | 4.5 | 0.5 | 5
64 | Constt. of road from Thalla to Birjala | ongoing | Baramulla | Uri | Thala | 0 | INFRA- I | 60 | 2016-17 | 2021-22 | 13.85 | 4.5 | 0.5 | 5
65 | Constt./Upgrd. Of Thala to Jabda road | ongoing | Baramulla | Uri | Jabda | 1 | INFRA- I | 80 | 2016-17 | 2021-22 | 12.07 | 4.5 | 0.5 | 5
66 | Constt. of Mugal mohalla to Kalgai Thala link | ongoing | Baramulla | Uri | Kalgai | 3 | INFRA- I | 90 | 2017-18 | 2021-22 | 9.06 | 4.5 | 0.5 | 5
67 | Constt. of road from Madian to Jabda via Alaphinda | ongoing | Baramulla | Uri | Jabda | 1 | INFRA- I | 90 | 2017-18 | 2021-22 | 10.5 | 4.5 | 0.5 | 5
68 | Constt. of road from Dachi main road to Muqam incld. Upper Dachi | ongoing | Baramulla | Uri | Dachi | 3 | INFRA- I | 75 | 2017-18 | 2021-22 | 11.77 | 4.5 | 0.5 | 5
69 | Constt. of road from main Choolan to Lower gingle | ongoing | Baramulla | Uri | Choolan | 1 | INFRA- I | 57 | 2017-18 | 2021-22 | 14.61 | 3.6 | 0.4 | 4
70 | Constt. of PMGSY road to High School Zamboor Pattan Link | ongoing | Baramulla | Uri | Choolan | 1 | INFRA- I | 60 | 2017-18 | 2021-22 | 10.77 | 3.6 | 0.4 | 4
71 | Road from Thajal PMGSY road to Food Store | ongoing | Baramulla | Uri | Thajal | 1 | INFRA- I | 25 | 2017-18 | 2020-21 | 9.07 | 3.6 | 0.4 | 4
72 | Constt. of main road uri to Lower Uri upto College Ground | ongoing | Baramulla | Uri | Uri | 5 | INFRA- I | 50 | 2017-18 | 2021-22 | 9.07 | 4.5 | 0.5 | 5
73 | Const. of PMGSY road to Bani | ongoing | Baramulla | Uri | Bani | 1 | INFRA- I | 114 | 2017-18 | 2022-23 | 10.76 | 4.5 | 0.5 | 5
74 | Const. Of PMGSY road to Jabla link road | ongoing | Baramulla | Uri | Jabla | 2 | INFRA- I | 40 | 2017-18 | 2021-22 | 8.23 | 4.5 | 0.5 | 5
75 | Widening / Extension of Bandi Dayar link road | ongoing | Baramulla | Uri | Dayar | 5 | INFRA- I | 76 | 2017-18 | 2022-23 | 10.77 | 4.5 | 0.5 | 5
76 | Constt. of link road from Beacon road to Sheikh Mohalla Gingle-Uri | ongoing | Baramulla | Uri | Gingle | 4 | INFRA- I | 33 | 2017-18 | 2020-21 | 11.77 | 4.5 | 0.5 | 5
77 | Const. of link road from National High Way upto Bhat Mohalla Nowpora Salamabad | ongoing | Baramulla | Uri | Slamabad | 4 | INFRA- I | 35 | 2017-18 | 2020-21 | 6.99 | 4.5 | 0.5 | 5
78 | Constr. Of Main road Choolan to Gali Daragutliyan. | ongoing | Baramulla | Uri | Daragutliyan | 3 | INFRA- I | 57.25 | 2018-19 | 2021-22 | 3 | 4.5 | 0.5 | 5
79 | Construction of road from R&B Store to Brinjan. | ongoing | Baramulla | Uri | Brijan | 3 | INFRA- I | 50 | 2018-19 | 2021-22 | 2 | 4.5 | 0.5 | 5
80 | Constr. Of road from Main road Zamboor Pattan Shukrlari to Bani | ongoing | Baramulla | Uri | Bani | 3 | INFRA- I | 48.05 | 2018-19 | 2021-22 | 2.2 | 4.5 | 0.5 | 5
81 | Constr. Of road from Main road Naganari to Chakan. | ongoing | Baramulla | Uri | Chakan | 4 | INFRA- I | 40 | 2018-19 | 2021-22 | 2.5 | 4.5 | 0.5 | 5
82 | Constr. Of Mughal road to Mir Mohalla Pringle. | ongoing | Baramulla | Uri | Pringle | 4 | INFRA- I | 15 | 2018-19 | 2020-21 | 2 | 1.8 | 0.2 | 2
83 | Constr. Of Mir Mohalla Link road at Mayan. | ongoing | Baramulla | Uri | Mayan | 5 | INFRA- I | 45 | 2018-19 | 2021-22 | 2 | 4.5 | 0.5 | 5
84 | Constr. Of link road from Dakan to Lohar/ Chachi/ Bhat Mohalla | ongoing | Baramulla | Uri | Dakan | 4 | INFRA- I | 95 | 2018-19 | 2021-22 | 2.02 | 4.5 | 0.5 | 5
85 | Constr. Of Main road Ghati to Ghati Mohalla at Daragutliyan. | ongoing | Baramulla | Uri | Daragutliyan | 3 | INFRA- I | 56 | 2018-19 | 2021-22 | 2.01 | 4.5 | 0.5 | 5
86 | WSS Karoone | ongoing | Baramulla | Uri | Karoone | 4 | INFRA- II | 40 | 2016-17 | 2021-22 | 7.25 | 4.5 | 0.5 | 5
87 | WSS Fatehwali | ongoing | Baramulla | Uri | Fatehwali | 4 | INFRA- II | 30 | 2016-17 | 2020-21 | 6.38 | 4.5 | 0.5 | 5
88 | WSS Deccan (Ward 7 & 8) | ongoing | Baramulla | Uri | Deccan | 4 | INFRA- II | 35 | 2016-17 | 2020-21 | 9.38 | 4.5 | 0.5 | 5
89 | Improvement / Extension of of WSS Gingle ,Dawaran and Zamboor Pattan | ongoing | Baramulla | Uri | Gingle | 4 | INFRA- II | 30 | 2016-17 | 2020-21 | 11.96 | 4.5 | 0.5 | 5
90 | Mohra Khandewan Khul | ongoing | Baramulla | Uri | Mohra | 3 | AGRI | 20 | 2016-17 | 2019-20 | 8.98 | 9.92 | 1.1 | 11.02
91 | Construction of Sub Centre with ANM Residence at Basgran Uri | ongoing | Baramulla | Uri | Basgran | 2 | HEALTH | 42.74 | 2016-17 | 2020-21 | 23.06 | 4.5 | 0.5 | 5
92 | Construction of Sub Centre with ANM Residence at Salamabad Uri | ongoing | Baramulla | Uri | Salamabad | 4 | HEALTH | 42.74 | 2016-17 | 2020-21 | 23.53 | 4.5 | 0.5 | 5
93 | Construction of Sub Centre with ANM Residence at Dardkote Uri | ongoing | Baramulla | Uri | Salamabad | 4 | HEALTH | 42.74 | 2016-17 | 2020-21 | 22.9 | 4.09 | 0.45 | 4.54
94 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | ongoing | Baramulla | Uri | All villages of Particular Block are eligible |  | SOCIAL | 87.72 |  | 2020-21 | 72.72 | 4.5 | 0.5 | 5
95 | Creation of 02 Nos of 100 KVA sub station at Salamabad,Uri | New | Baramulla | Uri | Salamabad,Uri | 2 | SOCIAL | 16 | 2019-20 | 2019-20 | 0 | 14.4 | 1.6 | 16
96 | Creation of 63 KVA substation 4 Nos at Dawaran,Dardkote,Kamalkote and Garkot | New | Baramulla | Uri | Dawaran,Dardkote,Kamalkote,Garkote, | 3 | SOCIAL | 20 | 2019-20 | 2020-21 | 0 | 6.3 | 0.7 | 7
97 | Augumentation of to WSS Hail by way of tapping of additional source (Spring) through pipe network and construction of addtional clear Water Sump at existing Pump Station Hail. | ongoing | Baramulla | Wagoora | Hail | 9 | INFRA- II | 40 | 2016-17 | 2019-20 | 30.73 | 8.34 | 0.93 | 9.27
98 | Construction of 2 No. Zonal SR's of 0.25 lac gallan capacity each at higher contour of Sheikhpora and Putuhar incld. Laying fitting of clear water main and supply main | ongoing | Baramulla | Wagoora | Khaipora | 3 | INFRA- II | 65 | 2016-17 | 2021-22 | 24.92 | 5.4 | 0.6 | 6
99 | SKILL DEV. PROGRAMME ( HANDICRAFTS,Handloom, Tourism, Health (FMPHW/ANM, Medical Assistant/ Pharmacy Assistant, O.T Assistant, etc)ITI courses | ongoing | Baramulla | Wagoora | villages of the Block | within 10 kms | SOCIAL | 10.2 | 2018-19 | 2019-20 | 5.7 | 4.05 | 0.45 | 4.5
100 | Constt. of Nilsar-Takia Yousuf Shah Wahizabal road | ongoing | Baramulla | Wagoora | Nilsar/ Takia Yousuf shah | 6 | INFRA- I | 133.62 | 2015-16 | 2021-22 | 48.37 | 5.4 | 0.6 | 6
101 | Constt. of link road Kachwa - Masjid Angan | ongoing | Baramulla | Wagoora | Kachwa/Masjid Anagan | 10 | INFRA- I | 152.55 | 2015-16 | 2021-22 | 47.67 | 6.69 | 0.74 | 7.43
102 | Waripora Waza Mohalla- Parray Mohalla Suchlipora road | ongoing | Baramulla | Wagoora | Waripora / Suchlipora | 8 | INFRA- I | 98.08 | 2015-16 | 2021-22 | 45.91 | 5.4 | 0.6 | 6
103 | Sherkhan patti-Shirpora Beigh Pati road | ongoing | Baramulla | Wagoora | Shirpora | 7 | INFRA- I | 162.98 | 2015-16 | 2021-22 | 36.67 | 5.4 | 0.6 | 6
104 | Putnar Saloosa road | ongoing | Baramulla | Wagoora | Saloosa | 10 | INFRA- I | 80 | 2016-17 | 2021-22 | 42.16 | 6.43 | 0.72 | 7.15
105 | Creation of sub 05 No. of Sub station at Muran Tangawari, Dungdara, Bed Check Kreeri, Watergam and Vizer. | New | Baramulla | Wagoora | Muran Tangawari, Dungdara, Bed Check Kreeri, Watergam and Vizer. | 8 | SOCIAL | 24.77 | 2019-20 | 2020-21 | 0 | 5.24 | 0.58 | 5.82
| Grand Total | [10 empty] | 504.11 | 56 | 560.11